## tandem_points_19-7-19_01-24
NC Status | MSN | Constituent Assembly (CA) | Natco Type | Reference | Description | Escalation Priority | Escalation Status | Comment | Conversation | Deadline Date | Tag
| 9151 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9151 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9274 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH Kl rung TAI erforderlich | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9196 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9220 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH Sealant mit PARA an HAM gesteuert | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9220 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH Sealant mit PARA an HAM gesteuert | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9214 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9214 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9208 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | TAI Window MOD MAIL TAI | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9208 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | TAI Window MOD MAIL TAI | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9248 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9248 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9285 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9285 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus
| 9016 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI wf stamped para from AiB
| 9074 | DH560 | CO-CO | TAI-005476523 | TAI-005476523 |  |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 |  | HH-RSP-No access
| 9057 | DH560 | CO-CO | TAI-005475463 | TAI-005475463 |  |  |  | Next access expected 15.08 - 19.08 S1 |  | HH-RSP-No access
| 9165 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N014537 AIRBUS REF. NC 14371908 |  |  | 04 07 2019 THC6BS - C64 P32LH Bohrl ufer in der Aussenhaut | TAI-005479239 concession created |  | HH-RSP-Prod
| 9016 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Shardul JOSHI wf stamped para from AiB
| 9079 | DH560 | OW-F5 | DH560-0003-005 | TAI QAR N014653 AIRBUS REF. NC 14348414 |  |  | 09 07 2019 NG7A244 -TAI to close Folio. Job done by PAG acc. to ref PARA D 53 TAI 19 9079 002 B 132 000 08.07. | Tolga BALCI Closure request raised 2 weeks ago Please close the point |  | HH-RSP-Admin
| 9251 | DH560 | OW-F5 | DH560-0003-001 | Lufthansa Paint issue. TAI COMO CT1502668-TAI-A-5234-A. Barrel will be |  |  | Lufthansa Paint issue . OS final durch Airbus HAM | Lufthansa Paint issue . OS final durch Airbus HAM
| 9300 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | MOD wird auf der n chsten Station umgesetzt | MOD wird auf der n chsten Station umgesetzt
| 9251 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Mod auf der n chsten Station umgesetzt
| 8992 | DH660 | CO-CO | TAI-005444050 | TAI-005444050 |  |  | Delle Beule an C64 to C65 P19-20 LH DOKU TAI-005444050 fully signed. | NC will be closed after AC control by TAI. No access next access 19.07 |  | HH-RSP-Admin
| 8992 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N009975 AIRBUS REF. NC 14311689 |  |  | Delle Beule an C64 to C65 P19-20 LH DOKU TAI-005444050 fully signed. | NC will be closed after AC control by TAI. No access next access 19.07 |  | HH-RSP-Admin
| 8776 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N005110 AIRBUS REF. NC 14244552 |  |  | REF. NC 14244552 | Next access H241-1 LH 27.08 - 08.09 S2 |  | HH-RSP-No access
| 8785 | DH560 | OW-F5 | DH560-0003-007 | TAI QAR N004313 AIRBUS REF. NC 14235449 |  |  |  | Next access St.21 17 - H 7.4 - L1 07.08 - 09.08 S1 |  | HH-RSP-No access
| 9074 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N014567 AIRBUS REF. NC 14381001 |  |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 |  | HH-RSP-No access
| 9057 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N009901 AIRBUS REF. NC 14318373 |  |  | C73 P24-P27 LH. Sealant and paint from Cleat cracked. | Next access expected 15.08 - 19.08 S1 |  | HH-RSP-No access
| 9044 | DH660 | CO-CO | TAI-005447419 | TAI-005447419 |  |  | Work DONE. ONLY PW. | TAI-005472633 Returned | 2019-06-21 | HH-RSP-Prod HH-RSP-PARA
| 9044 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N010504 AIRBUS REF. NC 14324706 |  |  | Rework completely done. ONLY PW due to the update of the NC and creatoin of the new CO for the RH dent. As soon as the RH CO is fully signed - all relevant PW will be closed. | TAI-005472633 Returned | 2019-06-21 | HH-RSP-Prod
| 9173 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N014591 AIRBUS REF. NC 14383305 |  |  | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done -- TAI-005476805 polish out NDT paint | TAI if access will be provided during holidays - rework will be performed during this time. See ref.NC 14383305 |  | HH-RSP-Prod HH-RSP-No access
| 9173 | DH560 | CO-CO | TAI-005476805 | TAI-005476805 |  |  | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done -- TAI-005476805 polish out NDT paint | TAI if access will be provided during holidays - rework will be performed during this time. See ref.NC 14383305 |  | HH-RSP-No access
| 9264 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015250 AIRBUS REF. NC 14384206 |  |  | 18 07 2019 th67s0 - work done - only docu NC 14384206 is closed | work done - only docu NC 14384206 is closed
| 9165 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Inflow QG-I | Ertan Akalin WF stamped para for folio closure from Airbus Oner SOYER | 2019-07-09 | HH-RSP-PARA
| 9165 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Inflow Qg-I | Ertan Akalin WF stamped para for folio closure from Airbus Oner SOYER | 2019-07-09 | HH-RSP-PARA
1 | 8836 | DA999 | QN-NC | 14310230 | Dent on FWD Fuselage |  |  |  | Katerina Sludnaya no acess next access Katerina will inform us. |  | HH-RSP-No access
2 | 8785 | DA999 | QN-NC | 14248201 | PPC Dent on Skin Sec. 19 |  | FAL HAM - Partner MFT |  | Katerina Sludnaya TAI to review area PARA couldn t be issued due to lack of information. Next Access 05.08 |  | HH-RSP-PARA HH-RSP-TBC HH-RSP-No access
1 | 8836 | DA999 | QN-NC | 14309898 | PPC Dent on Skin Sec. 19 |  |  |  | Katerina Sludnaya no acess next access Katerina will inform us. |  | HH-RSP-No access
1 | 9171 | DH550 | QN-NC | 14353693 | Inc DAS QR1 Joggle position |  |  | C64 - C65 RH P24 Stringer with wrong shape einstalled - work is done. | Katerina Sludnaya there is a technical problem at this point. We are trying the solve problem. |  | HH-RSP-Admin
1 | 9063 | DH000 | QN-NC | 14386351 | PNE Insp H8 CP6.0 |  |  |  | Nils Bostelmann no access next access 05.09.2019
| 8985 | DH630 | OW-F5 | DH630-0003-003 | TAI QAR N008048 AIRBUS REF. DR 400071478 |  |  | TAI QAR N008048 AIRBUS REF. DR 400071478 | Pascal JUNG Bitte hier eine status geben. |  | HH-RSP-PARA
| 9171 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N011698 AIRBUS REF. DR 400073823 |  |  | work done by RUAG mail | Pascal JUNG Please provide status. |  | HH-RSP-PARA
| 8961 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH MAIL | Shardul JOSHI Airbus responsibility window frame mod. W F Airbus Operation. |  | HH-RSP-Admin
1 | 8785 | DA999 | QN-NC | 14235449 | Sec.19 LH surface anomalie scratches |  |  |  | Shardul JOSHI AC in storage. Not possible to measure. |  | HH-RSP-No access
| 8961 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH MAIL | Shardul JOSHI Airbus responsibility window frame mod. W F Airbus Operation. |  | HH-RSP-Admin
1 | 8836 | DH000 | QN-NC | 14273155 | Dichtmasse fehlt Sekt.19 |  |  | In der Sektion 19 zwischen C73 und C74 fehlen bei diverse Massehalter Dichtmasse. - exch. TAI | Tolga BALCI Oner SOYER No access today. Waiting for the next slot. Info will be provided by FAL I will inform you | 2019-03-20 | HH-RSP-No access
| 8785 | DH560 | CO-CO | TAI-005419069 | TAI-005419069 |  |  |  | AC in storage Next Access 02.09 |  | HH-RSP-PARA HH-RSP-No access
3 | 9165 | DH000 | QN-NC | 14387488 | Fensterrahmenabdichtung |  |  | Inflow Qg-I | AIB Spain |  | HH-RSP-AiB Action
2 | 9208 | DH000 | QN-NC | 14387577 | Struktur BU passt nicht zur BUAusr stung |  |  | C65-66 P40-42 RH 2x bracket missing for compressor bracket item 110 iaw drawing to install | Bracket montiert neue BU muss erstellt werden f r TAI
1 | 9210 | DH000 | QN-NC | 14389316 | Besch digung T rrahmen Fremd |  |  | 11 07 2019 th67ag - C66 - C68 T rrahmen LH RH Besch digung Fremd | C66 - C68 T rrahmen LH RH Besch digung Fremd
1 | 9231 | DH560 | QN-NC | 14388629 | Damage at section 19 |  |  | 15 07 2019 TH67HG - C73 P 20-P 21 and P 24-P 32 RH the Sealant and paint from Cleat cracked | C73 P 20-P 21 and P 24-P 32 RH the Sealant and
1 | 9243 | DH560 | QN-NC | 14388811 | CPB 6035158 Findings Sec.19 |  |  | 15 07 2019 th67ag - C73 P15 - P17 LH RH Besch digungen | C73 P15 - P17 LH RH
| 9208 | DH630 | CO-CO | TAI-005481674 | TAI-005481674 |  |  | C65-C66 P40-P42 RH wrong fastner installed | CO wird gel scht
1 | 9057 | DH000 | QN-NC | 14318373 | Damage at section 19 |  | FAL HAM - LEVEL 1 - MSN-MFT LEVEL 2 - LINE-MFT | Inflow QG-I | Concession ACC. Next Access 15.08 - 19.08 |  | HH-RSP-No access
| 9204 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | DASL Abarbeitung in AM 14.08
| 9204 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | DASL Abarbeitung in AM 14.08
| 9247 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 15 07 2019 THC6BS -Die MOD wird auf der n chsten Station umgesetzt | Die MOD wird auf der n chsten Station umgesetzt
| 9247 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 15 07 2019 THC6BS - Die MOD wird auf der n chsten Station umgesetzt | Die MOD wird auf der n chsten Station umgesetzt
1 | 9214 | DH550 | QN-NC | 14385609 | Inc DAS QR41 damaged sealing |  |  |  | EXC
| 9312 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Fenstermod Nacharbeit TAI erf. | Fenstermod
| 9312 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 15 07 2019 THC6BS - Fenstermod Nacharbeit TAI erf. | Fenstermod
1 | 9044 | DH550 | QN-NC | 14324706 | Inc DAS QR39 Dent |  | FAL HAM - Partner MFT LEVEL 1 - MSN-MFT | 04 07 2019 THC5G6 - This CO for RH dent created additionally due to the update of the NC . CO LH TAI-005447419 is fully signed. CO RH TAI-005472633 is still i.P. Rework completely DONE dress out NDT . ONLY PW. NC will be closed when CO RH fully signed. | In clarification with quality | 2019-06-17 | HH-RSP-Prod
| 9300 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 15 07 2019 THC6BS - MOD wird auf der n chsten Station umgesetzt | MOD wird auf der n chsten Station umgesetzt
| 8953 |  | CR-QLB | SA.8953-0055 | HAM 04.04.10 SEC 19 LH FR 77 STR 17 |  |  | C77 P17 schramme innen the structure part must be check by TAI | Mail sent to Katerina to closure help
1 | 9141 | DZ000 | QN-NC | 14379616 | C Hatrack |  | FAL HAM - LEVEL 2 - LINE-MFT Partner MFT |  | Measurement taken on AC. Waiting for MAP desicion |  | HH-RSP-Prod
| 9251 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Mod auf der n chsten Station umgesetzt
2 | 9106 | DH000 | QN-NC | 14389457 | Scratches |  |  | C65-C66 P9 RH. Kerbe au en | NC beauftragt mit FAUF 200389789. 2x Kerbe im Bereich C65-C66 P9 RH au en auspolieren NDT dturchf hren QS Nacharbeit bewerten OS herstellen.
1 | 8992 | DH550 | QN-NC | 14311689 | D-Inc DAS QR1 Dent Impact |  |  | Delle Beule an C64 to C65 P19-20 LH DOKU TAI-005444050 fully signed. | NC will be closed after AC control by TAI. No access next access 19.07 |  | HH-RSP-Admin
| 8836 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N005566 AIRBUS REF. NC 14260346 |  |  | 02 07 2019 NG7A244 - TA provided PARA to PAG AUG. Work planned for 03 04.07 | NO ACCESS NEXT ACCESS KATERINA WILL INFORM |  | HH-RSP-PARA HH-RSP-No access
| 8836 | DH560 | OW-F5 | DH560-0003-005 | TAI QAR N006547 AIRBUS REF. NC 14273155 |  |  | In der Sektion 19 zwischen C73 und C74 fehlen bei diverse Massehalter Dichtmasse | NO ACCESS NEXT ACCESS KATERINA WILL INFORM |  | HH-RSP-No access
| 8836 | DH560 | CO-CO | TAI-005431941 | TAI-005431941 |  |  |  | NO ACCESS NEXT ACCESS KATERINA WILL INFORM. Related NC14260346 |  | HH-RSP-PARA HH-RSP-No access
1 | 8836 | DH000 | QN-NC | 14260346 | 1 Beule Aussen nach Innen |  | FAL HAM - Partner MFT resolved | 05 07 2019 THC5G6 - PARA no D 53 TAI 19 8836 003 B 132 000 TAI an PAG | NO Access today. Waiting for the next OSW slot - Info will be provided by the FAL. | 2019-02-14 | HH-RSP-PARA HH-RSP-No access
1 | 9041 | DH000 | QN-NC | 14362211 | eQLB 9041-0050 |  | FAL HAM - LEVEL 1 - MSN-MFT | The sealant from inside on the spring is not applied yet and will be finished in the next access. Work INCL. dry time will take 5 hrs. NOT paint relevant | Next access H.14-W - Dock L3 OSW 26.08 - 28.08 S1 |  | HH-RSP-No access
1 | 8774 | DH000 | QN-NC | 14198985 | MI000020017 Kratzer oder Bearbeitungsrie |  | DA - FAL HAM - OLE Cabin LEVEL 2 - LINE-MFT | 2 shifts | Next access H246-3-CT 22.08 - 23.09 S1 | 2019-05-03 | HH-RSP-No access
1 | 9074 | DA999 | QN-NC | 14381001 | PPC dent on skin Sec. 19 RH |  |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 |  | HH-RSP-No access
1 | 8906 | DA999 | QN-NC | 14375755 | in acc. to EQLB SA.8906-0003 |  |  |  | Next access planned for 09.08 - 13.08 S1 |  | HH-RSP-No access
2 | 9086 | DA999 | QN-NC | 14380001 | Delta-P PAX door 4 LH |  |  |  | Next access plannend H.14-W - Dock L3 14.08 - 16.08 S1 |  | HH-RSP-No access
| 8836 | DH560 | OW-F5 | DH560-0003-007 | TAI QAR N014662 AIRBUS REF. NC 14309898 |  |  |  | No Access. Next Access to be Confirmed |  | HH-RSP-Prod HH-RSP-No access
| 8785 | DH560 | OW-F5 | DH560-0003-008 | TAI QAR N005013 AIRBUS REF. NC 14248201 |  |  |  | PARA couldn t be issued to Paint Shop. Next Access 05.08 OSW |  | HH-RSP-No access
| 8774 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N001513 AIRBUS REF. NC 14198985 |  | FAL HAM - Partner MFT | Besch digung Kerbe am Fr spant C68 P5 LH - TAI Nacharbeit. | Planned for 19.08.2019 due to access problems... | 2019-01-16 | HH-RSP-No access
3 | 8953 | DH000 | QN-NC | 14311256 | eQLB SA.8953-0048 |  |  | C75-76 nick in the shroud pipe Change done | QAR and Folio already closed. |  | HH-RSP-Admin
| 8985 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N007174 AIRBUS REF. DR 400072061 |  |  | Inflow Qg-I | RUAG Confirmed the work performed. Folio to be closed. |  | HH-RSP-PARA
| 10001 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | C64-C65 LH work line for rework of window according MOD 25020 | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020
| 9269 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020
| 9264 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020
| 9283 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 17 07 2019 th67s0 - Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020
| 9360 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 17 07 2019 th67s0 - Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020
| 9264 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863
| 9283 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 17 07 2019 th67s0 - Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863
| 9360 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 17 07 2019 th67s0 - Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863
3 | 9264 | DH620 | QN-NC | 14385928 | Tool mark on skin with missing material |  |  | Sec. 18 C64-C65 P15-P16 RH drill start on outer skin rework according MAP Spain statement blend out and new NDT-Test from NC 14385928 from Airbus Spain necessary | Sec. 18 C64-C65 P15-P16 RH drill start on outer skin rework according MAP Spain statement blend out and new NDT-Test from NC 14385928 from Airbus Spain necessary
1 | 9252 | DH000 | QN-NC | 14382326 | Kratzer oder Bearbeitungsriefen |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C65 P22-P23 RH scratch on outer skin | Sec. 18 C64-C65 P22-P23 RH scatch on outer skin rework TAI necessary
| 9252 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N015171 AIRBUS REF. NC 14382326 |  |  | 18 07 2019 th67s0 - Sec. 18 C64-C65 P22-P23 RH work line because of NC 14382326 scratch on outer skin | Sec. 18 C64-C65 P22-P23 RH work line because of NC 14382326 scratch on outer skin rework TAI necessary
| 9269 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863
1 | 9269 | DH000 | QN-NC | 14386432 | Kratzer |  |  | 16 07 2019 th67s0 - Sec. 18 C64-C66 P32-P33 LH 3x scratch on inside skin | Sec. 18 C64-C66 P32-P33 LH 3x scratch on inside skin rework TAI necessary
| 9261 | DH550 | OW-F5 | DH550-0003-001 | please check the GAP on the first joggle at stringer P 24 in the area of |  |  | Pr fauftrag f r Stringer berlappung C65 R H P 24 | Sec. 18 C65 P24 RH work line becasue of check the GAP on the first joggle at stringer rework TAI necessary
| 9219 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015103 AIRBUS REF. NC 14391937 |  |  | 17 07 2019 th67s0 - Sec. 18 C66-C68 P15-P23 LH RH work line becasue of NC 14391937 1x missing surface protection on sealant by door frame C68 LH and 1x sealant damaged on door frame C66 RH | Sec. 18 C66-C68 P15-P23 LH RH work line becasue of NC 14391937 1x missing surface protection on sealant by door frame C68 LH and 1x sealant damaged on door frame C66 RH rework TAI necessary
1 | 9283 | DH000 | QN-NC | 14393437 | Niet nicht konform |  |  | 17 07 2019 th67s0 - Sec. 18 C67 P6-P7 LH 1x rivet not fitting properly | Sec. 18 C67 P6-P7 LH 1x rivet not fitting properly rework TAI necessary
1 | 9283 | DH000 | QN-NC | 14393398 | Niet nicht konform |  |  | 17 07 2019 th67s0 - Sec. 18 C67 P6-P7 RH 1x rivet not installed | Sec. 18 C67 P6-P7 RH 1x rivet not installed rework TAI necessary
| 9264 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012606 AIRBUS REF. DR 400073960 |  |  |  | TAI
| 9212 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013204 AIRBUS REF. DR 400074206 |  |  | TAI QAR N013204 AIRBUS REF. DR 400074206 | TAI
| 9280 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014572 AIRBUS REF. DR 400074912 |  |  |  | TAI
| 9283 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014597 AIRBUS REF. DR 400074950 |  |  |  | TAI
| 9287 | DH000 | QN-NC | 14395674 | Randabstand |  |  |  | TAI Sec 18 RH C64-65 p6 small edge distance check
4W | 9071 | DH000 | QN-NC | 14341511 | Kratzer am Scuffplate |  |  | C66 - C68 RH P23 scratches on Pax door scuff plate -- polish out | TAI to close QAR and folio. Job done by AAA. |  | HH-RSP-Admin
3 | 9086 | DH000 | QN-NC | 14360170 | Scuff Plate |  |  | C66-68 P23 dent middle scuff plate | TAI AAA EoW inkl dry-time 28.06 S2. OK for Delta P planned for 29.6 |  | HH-RSP-Admin
1 | 9170 | DH000 | QN-NC | 14386100 | eqlb SA.9170-0049 - Blend out bad cond. |  |  | C68-C69 P 20-P 21 Blend out in bad condition | TAI AAA EoW 19.7 S1 |  | HH-RSP-Prod
1 | 9171 | DH000 | QN-NC | 14380178 | PCC Beule an der Regenrinne LH |  |  | C67 - C68 LH P8 - P9 dent on rain gutter t -0 2mm -- 1.NDT done -- PARA to dent doctor 117494815 -- work done -- NDT needed | TAI AAA NDT done. EOW 19.7 S1 |  | HH-RSP-Prod
1 | 8776 | DA999 | QN-NC | 14244552 | Delta-P leak LH 4 Pax door |  | FAL HAM - Partner MFT OLE Cabin | 01 02 2019 th39aw - NOINFODA | TAI AAA waiting for access. If repair rework possible - EOW 18.7 if replacement needed - work will be performed in WP Slot. |  | HH-RSP-No access
2 | 8930 | DA999 | QN-NC | 14315993 | Scuff Plate 4 LH |  |  | 15.04.19 THA08M wait for rework order from ME spain | TAI AAA work starts today. EOW planned for 19.07 S2 if the AC will be available until 20.00 p.m. . |  | HH-RSP-Prod
| 9157 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N013039 AIRBUS REF. DR 400073960 |  |  |  | TAI
| 9121 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH Sealant au en offen PARA an HAM | TAI Fenster MOD
| 9121 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH Sealant au en offen PARA an HAM | TAI Fenster MOD
1 | 9165 | DH550 | QN-NC | 14370232 | Inc DAS QR1 Joggle position |  |  | 09 07 2019 THB5Y7 - Mit TAI-005464861 abgearbeitet. | TAI PW closure today |  | HH-RSP-Admin
1 | 9173 | DH000 | QN-NC | 14383305 | PCC Kratzer C71 - C72 P 10 - P 11 RH |  |  | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done -- TAI-005476805 polish out NDT paint | TAI if access will be provided during holidays - rework will be performed during this time. |  | HH-RSP-No access
1 | 9170 | DH000 | QN-NC | 14386087 | eqlb SA.9170-0054 - Structure chafing |  |  | C67 P 36 Stringer has been found in contact to Frame Structure | TAI waiting for MAP statement. As soon as the disposition provided the rework will be launched. |  | HH-RSP-TBC
1 | 9165 | DH000 | QN-NC | 14371908 | Bohrl ufer in der Au enhaut |  |  | Inflow QG-I | TAI waiting for the Qulaity signature. | 2019-07-09 | HH-RSP-Prod HH-RSP-Admin
3 | 9060 | DH550 | QN-NC | 14314325 | D-Inc DAS QR01 RUAG Impact Surface |  | FAL HAM - LEVEL 1 - MSN-MFT | Inflow QG-I | This point will be checked by a DAYL painter | 2019-05-16 | HH-RSP-Admin
3 | 9105 | DA999 | QN-NC | 14374410 | Girt Bar does not lock |  |  | 26 06 2019 THC5G6 - work done. PW only | To be closed by AID. Job done. NC closed. Folio closed. |  | HH-RSP-Admin
| 8774 | DH570 | CO-CO | TAI-005399985 | TAI-005399985 |  |  | 18 UPPER PANEL ASSEMBLY AT FRAME C68 BETWEEN | Work Planned for 19.08 | 2019-01-21 | HH-RSP-No access
| 9208 | DH630 | CO-CO | TAI-005481909 | TAI-005481909 |  |  | C66-C67 P40-P42 RH Dent MAIL TAI | Work done in AC
| 6673 | DH630 | OW-F5 | DH630-0003-002 | TAI QAR N014577 AIRBUS REF. NC 143881752 |  |  |  | Work is done with
1 | 9060 | DA999 | QN-NC | 14375859 | Hecksektion Hauptbolzen passt nicht |  | FAL HAM - LEVEL 1 - MSN-MFT |  | before Folio closure QAR must be deleted. Ata |  | HH-RSP-Admin
1 | 8964 | DH000 | QN-NC | 14334384 | SA.8964-0006 - Waviness and Toolmark |  | FAL HAM - Partner MFT | Waviness and Toolmark C65 P 21 RH | expected access 26.08 - 03.09 S1 |  | HH-RSP-No access
1 | 9171 | DH000 | QN-NC | 14383669 | Kratzer Aussenhaut C69-C70 |  |  | C69 - C70 RH P31 - P32 scratch -- 1. NDT done | job done NC closed. Folio to be closed. |  | HH-RSP-No access
| 9079 | DH560 | CO-CO | TAI-005474861 | TAI-005474861 |  |  |  | job done NC closed. close the CO. |  | HH-RSP-Admin
1 | 10001 | DH550 | QN-NC | 14370282 | Inc DAS QR1 Joggle position |  |  | C64-C65 P24 RH. Gap between Joggle and outer skin - TAI-005465567. | job done NC to be closed.
1 | 9167 | DH000 | QN-NC | 14364034 | Kratzer oder Bearbeitungsriefen |  |  | Kratzer oder Bearbeitungsriefen an C69 - C70 P7 - P8 LH | no access
1 | 9151 | DH550 | QN-NC | 14375023 | D-Inc DAS QR1 Scratch |  |  |  | no access for today
| 10001 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N015196 AIRBUS REF. NC 14374416 |  |  | Work done - only docu NC 14374416 closed. | work done - only docu NC 14374416 closed
| 9264 | DH620 | OW-F5 | DH620-0003-003 | TAI QAR N015253 AIRBUS REF. NC 14384206 |  |  | 18 07 2019 th67s0 - work done - only docu NC 14384206 is closed | work done - only docu NC 14384206 is closed
| 9269 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015133 AIRBUS REF. NC 14386432 |  |  |  | work line because of NC 14386432 scratch on skin panel rework TAI necessary
| 9112 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE.
| 9112 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE.
| 9274 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012845 AIRBUS REF. DR 400073960 |  |  | Kl rung TAI erforderlich
| 9042 | DH660 | CO-CO | TAI-005466579 | TAI-005466579 |  |  | C64 P19-20 LH Delle Beule - TAI-005466579
| 9274 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013209 AIRBUS REF. DR 400074255 |  |  | Kl rung TAI erforderlich
2 | 9095 | DH000 | QN-NC | 14374383 | Endpr fung Sealnaht-Besch digung |  |  | Endpr fung Sealnaht-Besch digung au en
| 9167 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012562 AIRBUS REF. DR 400074087
| 9187 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014576 AIRBUS REF. DR 400074914
| 9284 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE.
| 9284 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE.
| 9170 |  | CR-QLB | SA.9170-0049 | HAM07 19
| 9170 |  | CR-QLB | SA.9170-0054 | HAM07 19
1 | 9106 | DH000 | QN-NC | 14389602 | Scratches outer skin RH |  |  | C65-C66 P 10-P 11 RH. Scratches outer Skin.
1 | 9106 | DH000 | QN-NC | 14389633 | Tool mark |  |  | C65-C66 P19-P20 LH. Kratzer Au enhaut.