## maintandem
MSN | Constituent Assembly (CA) | Natco Type | Reference | Description | Comment | Old Conversation | Conversation | MY COMMENT | DETAILED COMMENT | STATUS
6673 | DH630 | OW-F5 | DH630-0003-002 | TAI QAR N014577 AIRBUS REF. NC 143881752 |  |  | Wrong NC number should be NC 14381752 | NEW 09.07 |  | OPEN
8774 | DH000 | QN-NC | 1.4198985E7 | MI000020017 Kratzer oder Bearbeitungsrie | 2 shifts |  | Next access H246-3-CT 22.08 - 23.09 S1 | NO ACCESS, NEXT ACCESS: 22.08.2019 - 23.09.2019 |  | OPEN
8774 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N001513 AIRBUS REF. NC 14198985 | Besch digung Kerbe am Fr spant C68 P5 LH - TAI Nacharbeit. |  | Planned for 19.08.2019 due to access problems... | NO ACCESS, NEXT ACCESS: 22.08.2019 - 23.09.2019 |  | OPEN
8774 | DH570 | CO-CO | TAI-005399985 | TAI-005399985 | 18 UPPER PANEL ASSEMBLY AT FRAME C68 BETWEEN |  | Work Planned for 19.08 | NO ACCESS, NEXT ACCESS: 22.08.2019 - 23.09.2019 |  | OPEN
8776 | DA999 | QN-NC | 1.4244552E7 | Delta-P leak LH 4 Pax door | 01 02 2019 th39aw - NOINFODA |  | Next access H241-1 LH 27.08 - 08.09 S2 | NO ACCESS, NEXT ACCESS: 27.08.2019 - 08.09.2019 |  | OPEN
8776 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N005110 AIRBUS REF. NC 14244552 | REF. NC 14244552 |  | Waiting for accces. Planned for 19.07.2019. | NO ACCESS, NEXT ACCESS: 27.08.2019 - 08.09.2019 |  | OPEN
8785 | DH560 | OW-F5 | DH560-0003-008 | TAI QAR N005013 AIRBUS REF. NC 14248201 |  |  | Next access St.21 17 - H 7.4 - L1 07.08 - 09.08 S1 | NO ACCESS, NEXT ACCESS: 05.08.2019 | WILL BE CHECKED ON MONDAY | OPEN
8785 | DH560 | OW-F5 | DH560-0003-007 | TAI QAR N004313 AIRBUS REF. NC 14235449 |  |  | Next access St.21 17 - H 7.4 - L1 07.08 - 09.08 S1 | NO ACCESS, NEXT ACCESS: 07.08.2019 - 09.09.2019 | WILL BE CHECKED ON MONDAY | OPEN
8785 | DA999 | QN-NC | 1.4235449E7 | Sec.19 LH surface anomalie scratches |  |  | Shardul JOSHI AC in storage. Not possible to measure. | NO ACCESS, NEXT ACCESS: 05.08.2019 |  | OPEN
8785 | DH560 | CO-CO | TAI-005419069 | TAI-005419069 |  |  | AC in storage Next Access 02.09 | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | OPEN
8785 | DA999 | QN-NC | 1.4248201E7 | PPC Dent on Skin Sec. 19 |  |  | Next access St.21 17 - H 7.4 - L1 07.08 - 09.08 S1 | NO ACCESS, NEXT ACCESS: 05.08.2019 | WILL BE CHECKED ON MONDAY | OPEN
8836 | DH000 | QN-NC | 1.4273155E7 | Dichtmasse fehlt Sekt.19 | In der Sektion 19 zwischen C73 und C74 fehlen bei diverse Massehalter Dichtmasse. - exch. TAI |  | Katerina Sludnaya could you pls inform us about next access | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DH560 | OW-F5 | DH560-0003-005 | TAI QAR N006547 AIRBUS REF. NC 14273155 | In der Sektion 19 zwischen C73 und C74 fehlen bei diverse Massehalter Dichtmasse |  | Next Access 25.11 St 21 | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N005566 AIRBUS REF. NC 14260346 | 02 07 2019 NG7A244 - TA provided PARA to PAG AUG. Work planned for 03 04.07 |  | PAG next access in H244 on 03. - 04.07. Access and IV will be clarified by Katerina S. | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DH000 | QN-NC | 1.4260346E7 | 1 Beule Aussen nach Innen | 17 06 2019 THC5G6 - CO TAI-005431941 fully signed. |  | next access in H244 on 03. - 04.07. Access and IV will be clarified by Katerina S. | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DH560 | CO-CO | TAI-005431941 | TAI-005431941 |  |  | next access in H244 on 03. - 04.07. Access and IV will be clarified by Katerina S. | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DH560 | OW-F5 | DH560-0003-007 | TAI QAR N014662 AIRBUS REF. NC 14309898 |  |  | No Access. Next Access to be Confirmed | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DA999 | QN-NC | 1.4309898E7 | PPC Dent on Skin Sec. 19 |  |  |  | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8836 | DA999 | QN-NC | 1.431023E7 | Dent on FWD Fuselage |  |  |  | NO ACCESS, NEXT ACCESS: KATERINA WILL INFORM |  | OPEN
8906 | DA999 | QN-NC | 1.4375755E7 | in acc. to EQLB SA.8906-0003 |  |  | Next access planned for 09.08 - 13.08 S1 | NEW 16.07.2019 |  | OPEN
8930 | DA999 | QN-NC | 1.4315993E7 | Scuff Plate 4 LH | 15.04.19 THA08M wait for rework order from ME spain |  | Work done.See NC | NO ACCESS, NEXT ACCESS: 18.07.2019 |  | OPEN
8950 | DA999 | QN-NC | 1.4346796E7 | Scratch on AFT Fuselage sec. 19 RH | 07 06 2019 THC5G6 - CO TAI-005461218 is fully signed |  | Next access H241-1 on 08.07 - 11.07 S1 | work done, NC and folio will be closed after final paint. |  | CLOSED
8953 |  | CR-QLB | SA.8953-0055 | HAM 04.04.10 SEC 19 LH FR 77 STR 17 | C77 P17 schramme innen the structure part must be check by TAI |  | Mail sent to Katerina to closure help | AIRBUS RESPONSIBILTY | KATERINA WILL HELP FOR CLOSURE, MAIL SENT. QLB | OPEN
8953 | DH000 | QN-NC | 1.4311256E7 | eQLB SA.8953-0048 | C75-76 nick in the shroud pipe Change done |  | QAR and Folio already closed. | AIRBUS RESPONSIBILTY | DH000 FOLIO POINT, WE CANT CLOSE, AIRBUS WILL CLOSE AFTER OPERATIONS. | OPEN
8961 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH MAIL |  | Bilal DEMIR Oner SOYER AC completed Paint. Please initiate Folio closure procedure | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
8961 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH MAIL |  | Oner SOYER Initiate closure | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
8964 | DH000 | QN-NC | 1.4334384E7 | SA.8964-0006 - Waviness and Toolmark | Waviness and Toolmark C65 P 21 RH |  | expected access 26.08 - 03.09 S1 | NO ACCESS, NEXT ACCESS: 26.08.2019 - 03.09.2019 |  | OPEN
8969 | DA999 | QN-NC | 1.4348106E7 | in acc. to EQLB SA.8969-0013 | Mapping to be done by QS |  | Access in 246 2 RH on 04.07. S2 WP | accepted as is, NC and folio to be closed. |  | CLOSED
8985 | DH630 | OW-F5 | DH630-0003-003 | TAI QAR N008048 AIRBUS REF. DR 400071478 | TAI QAR N008048 AIRBUS REF. DR 400071478 |  | Tolga BALCI | JOB DONE | WAITING PARA FROM RUAG | OPEN
8985 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N007174 AIRBUS REF. DR 400072061 | Inflow Qg-I |  | Tolga BALCI Please initiate Folio Closure. | JOB DONE | WAITING PARA FROM RUAG (AIRBUS DA CALISMIS OLABILIR) | OPEN
8992 | DH660 | CO-CO | TAI-005444050 | TAI-005444050 | Delle Beule an C64 to C65 P19-20 LH |  | NC will be closed after AC control by TAI. No access next access 19.07 | NO ACCESS, NEXT ACCESS: 19.07.2019 |  | OPEN
8992 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N009975 AIRBUS REF. NC 14311689 | Delle Beule an C64 to C65 P19-20 LH |  | NC will be closed after AC control by TAI. No access next access 19.07 | NO ACCESS, NEXT ACCESS: 19.07.2019 |  | OPEN
8992 | DH550 | QN-NC | 1.4311689E7 | D-Inc DAS QR1 Dent Impact | 07 06 2019 THC5G6 - TAI-005444050 fully signed. |  | NC will be closed after AC control by TAI. No access next access 19.07 | NO ACCESS, NEXT ACCESS: 19.07.2019 |  | OPEN
9016 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI wf stamped para from AiB | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9016 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI wf stamped para from AiB | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9041 | DH000 | QN-NC | 1.4362211E7 | eQLB 9041-0050 | The sealant from inside on the spring is not applied yet and will be finished in the next access. Work INCL. dry time will take 5 hrs. NOT paint relevant |  | Next access H.14-W - Dock L3 OSW 26.08 - 28.08 S1 | NO ACCESS, NEXT ACCESS: 26.08.2019 - 28.08.2019 |  | OPEN
9042 | DH660 | CO-CO | TAI-005466579 | TAI-005466579 | C64 P19-20 LH Delle Beule - TAI-005466579 |  |  | AAA Resp. |  | OPEN
9044 | DH660 | CO-CO | TAI-005447419 | TAI-005447419 | Work DONE. ONLY PW. |  | Tolga BALCI PARA D53.ME-9044-001 was used to perform Rework on TAI NC 14324706 . Please follow up and provide an update and close FW. AiB HAM WO 117295615 closed | AAA wf co | SAME NC 2 NC`S LH & RH ISSUE WF CON. CLOOSURE | OPEN
9044 | DH550 | QN-NC | 1.4324706E7 | Inc DAS QR39 Dent | 04 07 2019 THC5G6 - This CO for RH dent created additionally due to the update of the NC . CO LH TAI-005447419 is fully signed. CO RH TAI-005472633 is still i.P. Rework completely DONE dress out NDT . ONLY PW. NC will be closed when CO RH fully signed. |  | TAI CO TAI-005472633 i.P. PW ONLY | TAI Resp.-No access | SAME NC 2 NC`S LH & RH ISSUE WF CON. CLOOSURE | OPEN
9044 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N010504 AIRBUS REF. NC 14324706 | Rework completely done. ONLY PW due to the update of the NC and creatoin of the new CO for the RH dent. As soon as the RH CO is fully signed - all relevant PW will be closed. |  | Waiting for CO Cycle to be compelted. | AAA wf co |  | OPEN
9057 | DH000 | QN-NC | 1.4318373E7 | Damage at section 19 | Inflow QG-I |  | Next access expected 15.08 - 19.08 S1 | TAI wf MAP disp. |  | OPEN
9057 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N009901 AIRBUS REF. NC 14318373 | C73 P24-P27 LH. Sealant and paint from Cleat cracked. |  | S.Kommentar im Ref.Nc. 14318373 | NC number can not find. |  | OPEN
9057 | DH560 | CO-CO | TAI-005475463 | TAI-005475463 |  |  |  | Ok by TAI |  | OPEN
9060 | DH550 | QN-NC | 1.4314325E7 | D-Inc DAS QR01 RUAG Impact Surface | Inflow QG-I |  | This point will be checked by a DAYL painter | Ok by TAI wf MAP | NC OPEN This point will be checked by a DAYL painter | OPEN
9060 | DA999 | QN-NC | 1.4375859E7 | Hecksektion Hauptbolzen passt nicht |  |  | before Folio closure QAR must be deleted. Ata | Defected area is not resp. TAI | NC FROM DH999, AIRBUS WILL CLOSE THIS NC | OPEN
9063 | DH000 | QN-NC | 1.4386351E7 | PNE Insp H8 CP6.0 |  |  | TAI AAA will perform the job. WF access | AAA will perform the job 05.09.2019 | STARTED; WF AAA FOR HANDFORM | OPEN
9071 | DH000 | QN-NC | 1.4341511E7 | Kratzer am Scuffplate | C66 - C68 RH P23 scratches on Pax door scuff plate -- polish out |  | TAI to close QAR and folio. Job done by AAA. | AAA Resp. | NC FROM DH000, AIRBUS WILL CLOSE THIS NC | OPEN
9074 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N014567 AIRBUS REF. NC 14381001 |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 | PAG Resp. |  | OPEN
9074 | DA999 | QN-NC | 1.4381001E7 | PPC dent on skin Sec. 19 RH |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 | TAI will work 12.07.2019 |  | OPEN
9074 | DH560 | CO-CO | TAI-005476523 | TAI-005476523 |  |  |  | ABS Resp. |  | OPEN
9079 | DH560 | CO-CO | TAI-005474861 | TAI-005474861 |  |  | FW to be crossed out | AAA Resp. |  | OPEN
9079 | DH560 | OW-F5 | DH560-0003-005 | TAI QAR N014653 AIRBUS REF. NC 14348414 | 09 07 2019 NG7A244 -TAI to close Folio. Job done by PAG acc. to ref PARA D 53 TAI 19 9079 002 B 132 000 08.07. |  | job done NC closed folio to be closed | Ok by TAI wf MAP |  | OPEN
9086 | DH000 | QN-NC | 1.436017E7 | Scuff Plate | C66-68 P23 dent middle scuff plate |  | TAI AAA EoW inkl dry-time 28.06 S2. OK for Delta P planned for 29.6 | AAA Resp.wf access | NC FROM DH000, AIRBUS WILL CLOSE THIS NC | OPEN
9086 | DA999 | QN-NC | 1.4380001E7 | Delta-P PAX door 4 LH |  |  | TAI will perform the job. Could you pleas inform about Access Katerina Sludnaya | AAA Resp.wf access |  | OPEN
9095 | DH000 | QN-NC | 1.4374383E7 | Endpr fung Sealnaht-Besch digung | Endpr fung Sealnaht-Besch digung au en |  |  | AAA RESPONSIBILTYONSIBILTY |  | OPEN
9105 | DA999 | QN-NC | 1.437441E7 | Girt Bar does not lock | 26 06 2019 THC5G6 - work done. PW only |  | To be closed by AID. Job done. NC closed. Folio closed. | AIRBUS RESPONSIBILTY | To be closed by AID. Job done. NC closed. Folio closed. | OPEN
9108 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012240 AIRBUS REF. NC 14346528 | C64 65 P 24 RH. Fehlerhafter Stringer |  | Shardul JOSHI need stamped para from Airbus | AIRBUS RESPONSIBILTY | C64/65 P'24 RH. Fehlerhafter Stringer | CLOSED
9112 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9112 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9121 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | TAI Fenster MOD | AIRBUS RESPONSIBILTY |  | OPEN
9121 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | TAI Fenster MOD | AIRBUS RESPONSIBILTY |  | OPEN
9141 | DZ000 | QN-NC | 1.4379616E7 | C Hatrack |  |  | Measurement taken on AC. Waiting for MAP desicion | AAA RESPONSIBILTY | WF CONCESSION | OPEN
9151 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9151 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9151 | DH550 | QN-NC | 1.4375023E7 | D-Inc DAS QR1 Scratch |  |  |  | NO ACCESS; NEXT ACCESS. |  | OPEN
9157 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N013039 AIRBUS REF. DR 400073960 |  |  | TAI | NEW 16.07.2019 |  | OPEN
9165 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 24 06 2019 THC6BS - Fenster mod |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9165 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 04 07 2019 THC6BS - Fenster mod |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9165 | DH000 | QN-NC | 1.4371908E7 | Bohrl ufer in der Au enhaut | 24 06 2019 THC6BS - C64 P32LH Anbohrung L ufer in der Aussenhaut |  | DASL C64 P32 LH 1x Bohrung offen Bohrl ufer in der Au enhaut | AAA RESPONSIBILTYONSIBILTY | WF CONCESSION | OPEN
9165 | DH550 | QN-NC | 1.4370232E7 | Inc DAS QR1 Joggle position | 24 06 2019 THC6BS - C65-C64 RH P 24 RH falscher Stringer montiert |  | stringer Airbus will perform the job. | AIRBUS RESPONSIBILTY |  | OPEN
9165 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N014537 AIRBUS REF. NC 14371908 | 04 07 2019 THC6BS - C64 P32LH Bohrl ufer in der Aussenhaut |  | C64 P32LH | AAA RESPONSIBILTYONSIBILTY |  | OPEN
9165 | DH000 | QN-NC | 1.4387488E7 | Fensterrahmenabdichtung | Inflow Qg-I |  |  | AIRBUS RESPONSIBILTY | AIRBUS SPAIN | OPEN
9170 | DH000 | QN-NC | 1.4386087E7 | eqlb SA.9170-0054 - Structure chafing | C67 P 36 Stringer has been found in contact to Frame Structure |  | Waiting for MAP statement. Rework will be done by TAI | AIRBUS RESPONSIBILTY |  | OPEN
9170 |  | CR-QLB | SA.9170-0049 | HAM07 19 |  |  |  | NEW 10.07 |  | OPEN
9170 | DH000 | QN-NC | 1.43861E7 | eqlb SA.9170-0049 - Blend out bad cond. | C68-C69 P 20-P 21 Blend out in bad condition |  |  | AAA WILL PERFORM THE JOB | 15.07 DEADLINE. | OPEN
9170 |  | CR-QLB | SA.9170-0054 | HAM07 19 |  |  |  | NEW 10.07 |  | OPEN
9171 | DH000 | QN-NC | 1.4383669E7 | Kratzer Aussenhaut C69-C70 | C69 - C70 RH P31 - P32 scratch -- 1. NDT done |  | job done NC closed. folio to be closed | AAA WORKING. WF NDT |  | OPEN
9171 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N011698 AIRBUS REF. DR 400073823 | work done by RUAG mail |  | Pascal JUNG Please provide status. | NO PLAN |  | OPEN
9171 | DH550 | QN-NC | 1.4353693E7 | Inc DAS QR1 Joggle position | C64 - C65 RH P24 Stringer with wrong shape einstalled - work is done. |  | job done NC closed. folio to be closed | AIRBUS RESPONSIBILTY |  | OPEN
9171 | DH000 | QN-NC | 1.4380178E7 | PCC Beule an der Regenrinne LH | C67 - C68 LH P8 - P9 dent on rain gutter t -0 2mm -- 1.NDT done -- PARA to dent doctor 117494815 -- work done -- NDT needed |  | TAI AAA waiting for NDT access St42 on 12.07 | AAA WF NDT |  | OPEN
9173 | DH000 | QN-NC | 1.4383305E7 | PCC Kratzer C71 - C72 P 10 - P 11 RH | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done |  |  | NO ACCESS, NEXT ACCESS: 20.07.2019 |  | OPEN
9173 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N014591 AIRBUS REF. NC 14383305 | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done |  |  | NO ACCESS, NEXT ACCESS: 20.07.2020 |  | OPEN
9173 | DH560 | CO-CO | TAI-005476805 | TAI-005476805 | C71 - C72 RH P10 - P11 scratch t -0 07mm -- 1.NDT done -- TAI-005476805 polish out NDT paint |  |  | NO ACCESS, NEXT ACCESS: 20.07.2021 |  | OPEN
9187 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014576 AIRBUS REF. DR 400074914 |  |  |  | NO PLAN |  | OPEN
9196 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  | OPEN
9204 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9204 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9208 | DH000 | QN-NC | 1.4387577E7 | Struktur BU passt nicht zur BUAusr stung |  |  | no remaining phisical work. concession will be created for docu. Job done by TAI. NC will be closed. | job done by TAI NC closed. folio to be closed after co. Creation. |  | OPEN
9208 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  | OPEN
9208 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  | OPEN
9210 | DH000 | QN-NC | 1.4389316E7 | Besch digung T rrahmen Fremd | 11 07 2019 th67ag - C66 - C68 T rrahmen LH RH Besch digung Fremd |  | C66 - C68 T rrahmen LH RH Besch digung Fremd | NO PLAN |  | OPEN
9212 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013204 AIRBUS REF. DR 400074206 | TAI QAR N013204 AIRBUS REF. DR 400074206 |  | TAI | NO PLAN |  | OPEN
9214 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9214 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9214 | DH550 | QN-NC | 1.4385609E7 | Inc DAS QR41 damaged sealing |  |  | EXC | NO PLAN |  | OPEN
9220 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH Sealant mit PARA an HAM gesteuert |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  | OPEN
9220 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH Sealant mit PARA an HAM gesteuert |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  | OPEN
9231 | DH560 | QN-NC | 1.4388629E7 | Damage at section 19 | 15 07 2019 TH67HG - C73 P 20-P 21 and P 24-P 32 RH the Sealant and paint from Cleat cracked |  | C73 P 20-P 21 and P 24-P 32 RH the Sealant and | NO PLAN |  | OPEN
9243 | DH560 | QN-NC | 1.4388811E7 | CPB 6035158 Findings Sec.19 |  |  |  | NO PLAN |  | OPEN
9247 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 15 07 2019 THC6BS -Die MOD wird auf der n chsten Station umgesetzt |  | Die MOD wird auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9247 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 15 07 2019 THC6BS - Die MOD wird auf der n chsten Station umgesetzt |  | Die MOD wird auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9248 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9248 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9251 | DH560 | OW-F5 | DH560-0003-001 | Lufthansa Paint issue. TAI COMO CT1502668-TAI-A-5234-A. Barrel will be |  |  | Lufthansa Paint issue . OS final durch Airbus HAM | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS ACCORDING LUFTHANSA PAINT ISSUE | OPEN
9251 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Mod auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9251 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Mod auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9264 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY |  | OPEN
9264 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY |  | OPEN
9264 | DH620 | QN-NC | 1.4385928E7 | Tool mark on skin with missing material |  |  | Sec. 18 C64-C65 P15-P16 RH drill start on outer skin solution MAP Spain and rework TAI necessary | NO PLAN |  | OPEN
9264 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012606 AIRBUS REF. DR 400073960 |  |  | TAI | NO PLAN |  | OPEN
9269 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9269 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9269 | DH000 | QN-NC | 1.4386432E7 | Kratzer |  |  | TAI | NO PLAN | WF. MAP. DESP: | OPEN
9274 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9274 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012845 AIRBUS REF. DR 400073960 | Kl rung TAI erforderlich |  |  | NO PLAN |  | OPEN
9274 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013209 AIRBUS REF. DR 400074255 | Kl rung TAI erforderlich |  |  | NO PLAN |  | OPEN
9280 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014572 AIRBUS REF. DR 400074912 |  |  | TAI | NO PLAN |  | OPEN
9283 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY |  | OPEN
9283 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY |  | OPEN
9283 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014597 AIRBUS REF. DR 400074950 |  |  | TAI | NO PLAN |  | OPEN
9284 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | AIRBUS RESPONSIBILTY |  | OPEN
9284 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | AIRBUS RESPONSIBILTY |  | OPEN
9285 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9285 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | OPEN
9300 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | MOD wird auf der n chsten Station umgesetzt |  | MOD wird auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9300 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 15 07 2019 THC6BS - MOD wird auf der n chsten Station umgesetzt |  | MOD wird auf der n chsten Station umgesetzt | AIRBUS RESPONSIBILTY |  | OPEN
9312 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | Fenstermod Nacharbeit TAI erf. |  | Fenstermod | AIRBUS RESPONSIBILTY |  | OPEN
9312 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 15 07 2019 THC6BS - Fenstermod Nacharbeit TAI erf. |  | Fenstermod | AIRBUS RESPONSIBILTY |  | OPEN
9360 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY |  | OPEN
9360 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY |  | OPEN
10001 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY |  | OPEN
10001 | DH550 | QN-NC | 1.4370282E7 | Inc DAS QR1 Joggle position |  |  | work done from HAM according PARA D53 TA 18 10001 001 B 132 000 concession TAI-005465567 | NEW 16.07.2019 |  | OPEN
9252 | DH000 | QN-NC | 1.4382326E7 | Kratzer oder Bearbeitungsriefen | 16 07 2019 th67s0 - Sec. 18 C64-C65 P22-P23 RH scratch on outer skin |  | Sec. 18 C64-C65 P22-P23 RH scatch on outer skin rework TAI necessary | YENI 17.07.2019 |  | OPEN
9261 | DH550 | OW-F5 | DH550-0003-001 | please check the GAP on the first joggle at stringer P 24 in the area of | Pr fauftrag f r Stringer berlappung C65 R H P 24 |  | Sec. 18 C65 P24 RH work line becasue of check the GAP on the first joggle at stringer rework TAI necessary | YENI 17.07.2019 |  | OPEN
9283 | DH000 | QN-NC | 1.4393437E7 | Niet nicht konform |  |  | TAI | YENI 17.07.2019 |  | OPEN
9283 | DH000 | QN-NC | 1.4393398E7 | Niet nicht konform |  |  | TAI | YENI 17.07.2019 |  | OPEN
9264 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015250 AIRBUS REF. NC 14384206 | 18 07 2019 th67s0 - work done - only docu NC 14384206 is closed |  | work done - only docu NC 14384206 is closed | NEW 18.07.2019 |  | OPEN
9208 | DH630 | CO-CO | TAI-005481674 | TAI-005481674 | C65-C66 P40-P42 RH wrong fastner installed |  | CO wird gel scht | NEW 18.07.2019 |  | OPEN
9106 | DH000 | QN-NC | 1.4389457E7 | Scratches | C65-C66 P9 RH. Kerbe au en |  | NC beauftragt mit FAUF 200389789. 2x Kerbe im Bereich C65-C66 P9 RH au en auspolieren NDT dturchf hren QS Nacharbeit bewerten OS herstellen. | NEW 18.07.2019 |  | OPEN
9252 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N015171 AIRBUS REF. NC 14382326 | 18 07 2019 th67s0 - Sec. 18 C64-C65 P22-P23 RH work line because of NC 14382326 scratch on outer skin |  | Sec. 18 C64-C65 P22-P23 RH work line because of NC 14382326 scratch on outer skin rework TAI necessary | NEW 18.07.2019 |  | OPEN
9219 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015103 AIRBUS REF. NC 14391937 | 17 07 2019 th67s0 - Sec. 18 C66-C68 P15-P23 LH RH work line becasue of NC 14391937 1x missing surface protection on sealant by door frame C68 LH and 1x sealant damaged on door frame C66 RH |  | Sec. 18 C66-C68 P15-P23 LH RH work line becasue of NC 14391937 1x missing surface protection on sealant by door frame C68 LH and 1x sealant damaged on door frame C66 RH rework TAI necessary | NEW 18.07.2019 |  | OPEN
9287 | DH000 | QN-NC | 1.4395674E7 | Randabstand |  |  | TAI Sec 18 RH C64-65 p6 small edge distance check | NEW 18.07.2019 |  | OPEN
9208 | DH630 | CO-CO | TAI-005481909 | TAI-005481909 | C66-C67 P40-P42 RH Dent MAIL TAI |  | Work done in AC | NEW 18.07.2019 |  | OPEN
9167 | DH000 | QN-NC | 1.4364034E7 | Kratzer oder Bearbeitungsriefen | Kratzer oder Bearbeitungsriefen an C69 - C70 P7 - P8 LH |  | no access | NEW 18.07.2019 |  | OPEN
10001 | DH660 | OW-F5 | DH660-0003-003 | TAI QAR N015196 AIRBUS REF. NC 14374416 | Work done - only docu NC 14374416 closed. |  | work done - only docu NC 14374416 closed | NEW 18.07.2019 |  | OPEN
9264 | DH620 | OW-F5 | DH620-0003-003 | TAI QAR N015253 AIRBUS REF. NC 14384206 | 18 07 2019 th67s0 - work done - only docu NC 14384206 is closed |  | work done - only docu NC 14384206 is closed | NEW 18.07.2019 |  | OPEN
9269 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N015133 AIRBUS REF. NC 14386432 |  |  | work line because of NC 14386432 scratch on skin panel rework TAI necessary | NEW 18.07.2019 |  | OPEN
9167 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012562 AIRBUS REF. DR 400074087 |  |  |  | NEW 18.07.2019 |  | OPEN
9106 | DH000 | QN-NC | 1.4389602E7 | Scratches outer skin RH | C65-C66 P 10-P 11 RH. Scratches outer Skin. |  |  | NEW 18.07.2019 |  | OPEN
9106 | DH000 | QN-NC | 1.4389633E7 | Tool mark | C65-C66 P19-P20 LH. Kratzer Au enhaut. |  |  | NEW 18.07.2019 |  | OPEN

## Sheet1
NC | FOLIO | DATE
14379230 | / DH000 | 2019-06-28
14375023 | DH550 / | 2019-06-27
14375518 | / DH000 | 2019-06-27
14352558 | / DH000 | 2019-05-27
14375755 | / DA999 | 2019-06-25
14334384 | / DH000 | 2019-05-24
14370282 | DH550 / | 2019-06-21
14260346 | / DH000 | 2019-04-21
14318373 | / DH000 | 2019-06-20
14324706 | DH550 / | 2019-06-20
14370232 | DH550 / | 2019-06-20
14369845 | / DH000 | 2019-06-19
14364034 | / DH000 | 2019-06-18
14391829 | / DH000 | 2019-07-17
14362211 | / DH000 | 2019-06-17
14198985 | / DH000 | 2019-01-17
14345856 | / DH000 | 2019-07-16
14392258 | / DH000 | 2019-07-16
14380924 | / DH000 | 2019-07-16
14386100 | / DH000 | 2019-07-16
14387143 | / DZ000 | 2019-07-16
14393005 | / DH000 | 2019-07-16
14393398 | / DH000 | 2019-07-16
14393437 | / DH000 | 2019-07-16
14380739 | / DH000 | 2019-07-16
14393258 | / DA999 | 2019-07-16
14392758 | / DH000 | 2019-07-15
14392330 | / DH000 | 2019-07-15
14392340 | / DH000 | 2019-07-15
14391937 | / DH000 | 2019-07-15
14391650 | / DH000 | 2019-07-15
14392867 | / DH000 | 2019-07-15
14362409 | / DH000 | 2019-06-14
14364491 | / DH000 | 2019-06-14
14311689 | DH550 / | 2019-06-13
14389457 | / DH000 | 2019-07-12
14389633 | / DH000 | 2019-07-12
14388721 | DH550 / | 2019-07-12
14389294 | / DH000 | 2019-07-12
14356179 | DH550 / | 2019-07-12
14364079 | / DH000 | 2019-06-12
14315993 | / DA999 | 2019-07-11
14389316 | / DH000 | 2019-07-11
14386432 | / DH000 | 2019-07-11
14385751 | / DH000 | 2019-07-11
14360781 | / DH000 | 2019-06-11
14387577 | / DH000 | 2019-07-10
14388629 | / DH56 | 2019-07-10
14386916 | / DH000 | 2019-07-10
14385688 | / DH000 | 2019-07-10
14386259 | DH550 / | 2019-07-10
14387198 | / DH000 | 2019-07-10
14388811 | / DH56 | 2019-07-10
14388441 | / DH000 | 2019-07-09
14379616 | / DZ000 | 2019-07-09
14386351 | / DH000 | 2019-07-08
14386087 | / DH000 | 2019-07-08
14384206 | / DH000 | 2019-07-08
14385609 | DH550 / | 2019-07-08
14380001 | / DA999 | 2019-07-08
14273155 | / DH000 | 2019-04-08
14359884 | DH550 / | 2019-06-06
14348001 | / DH000 | 2019-07-05
14310230 | / DA999 | 2019-07-05
14309898 | / DA999 | 2019-07-05
14383109 | / DH000 | 2019-07-04
14383217 | / DH000 | 2019-07-04
14382326 | / DH000 | 2019-07-04
14382810 | / DH000 | 2019-07-04
14374383 | / DH000 | 2019-07-04
14374416 | / DH000 | 2019-07-04
14383305 | / DH000 | 2019-07-04
14353741 | / DH550 | 2019-06-04
14244552 | / DA999 | 2019-02-04
14381001 | / DA999 | 2019-07-03
14382465 | / DH56 | 2019-07-02
14371908 | / DH000 | 2019-07-02

## qar bekler
MSN | NC / DR | FOLIO | QAR / CO | STATU | TARIH
8985 | 400072061 | DH630-0003-001 | N007174 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9042 | 14346916 | DH660-0003-002 | N012772 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9079 | 14348414 | DH560-0003-005 | N014653 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9079 | 14375989 | DH560 | TAI-005474861
9093 | 14380300 | DH630-0003-002 | N014349 | QAR’ı açık olduğu için foliosu kapatılamıyor. QAR me’de
9108 | 14346528 | DH620-0003-001 | N012240 | QAR’ı açık olduğu için foliosu kapatılamıyor. QAR mrb de
9108 | 14346528 | DH620-0003-001 | N012240 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9149 | 14356658 | DH560-0003-003 | N012898
9170 | 14352558 | DH620-0003-001 | N012447 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9225 | 14380680 | DH620-0003-001 | N014395 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9235 | 14387092 | DH560-0003-001 | N014829 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9044 | 14324706 | DH660-0003-001 | N010504 | QAR’ı açık olduğu için foliosu kapatılamıyor.
8985 | 400072061 | DH630-0003-001 | N007174 | QAR’ı açık olduğu için foliosu kapatılamıyor.
9079 | 14348414 | DH560-0003-005 | N014653 | QAR’ı açık olduğu için foliosu kapatılamıyor.

## closed
MSN | Constituent Assembly (CA) | Natco Type | Reference | Description | Comment | Old Conversation | Conversation | MY COMMENT | DETAILED COMMENT | STATUS | ONER MAIL
8774 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N000367 AIRBUS REF. 400069364 | 18 06 2019 NG7A244 - TA waiting for Stamped PARA from RUAG. Awaiting closure clarification from TA |  | Request sent to RUAG to share stamped para | WF STAMPED PARA FROM RUAG SINCE 30.05.2019 |  |  | CLOSED
8864 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N004731 AIRBUS REF. NC 14247431 | NO ACCESS, NEXT ACCESS: 29.08.2019 |  | WE ARE WAITING FOR NC TO STEER BACK TO TAI POST BOX |  |  |  | CLOSED
8864 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N004740 AIRBUS REF. NC 14246223 | NO ACCESS, NEXT ACCESS: 29.08.2019 |  | WE ARE WAITING FOR NC TO STEER BACK TO TAI POST BOX |  |  |  | CLOSED
8898 | DH620 | OW-F5 | DH620-0003-001 | Green Card Operation 18D534-80505-069EX-GC2 DTS Change | C64-C65 P 23 RH. Struktur part to replace |  | Mods expected to be deleted by Airbus within this week. Then TAI will close folio. | AIRBUS RESPONSIBILTY | WE ARE WAITING REBECA TO DELETE MODS, FATIH SENT E-MAIL
8898 | DH620 | OW-F5 | DH620-0003-001 | Green Card Operation 18D534-80505-069EX-GC2 DTS Change | C64-C65 P 23 RH. Struktur part to replace |  | Mods expected to be deleted by Airbus within this week. Then TAI will close folio. | AIRBUS RESPONSIBILTY | WE ARE WAITING REBECA TO DELETE MODS, FATIH SENT E-MAIL | CLOSED
8906 | DA999 | QN-NC | 14375755 | in acc. to EQLB SA.8906-0003 |  |  | Next access planned for 19.07 - 07.08 S1 | NO ACCESS, NEXT ACCESS: 29.08.2019 |  |  | CLOSED
8911 |  | CR-QLB | SA.8911-0054 | HAM 29.03.2019 Section 19 FR72 77 LH RH | Final Paint HLW Anschlss |  | Katerina Sludnaya a kind reminder for closure | AIRBUS RESPONSIBILTY | KATERINA WILL HELP FOR CLOSURE, MAIL SENT. PAINT SHOP ISSUE | closed
8946 | DH000 | QN-NC | 14387589 | Fensterrahmen Abdichtung entgegen BU | Inflow Qg-I |  |  | NEW |  | CLOSED
8950 | DH000 | QN-NC | 14320267 | Besch digung Scuffplate | Paint APPLY THE SEALANT AT SCUFFPLATE IN AREA C68-C69 RH |  | TAI to check stamped PARA. Job done by AAA. | NO ACCESS, NEXT ACCESS: 08.07.2019 |  | closed
8950 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N012099 AIRBUS REF. NC 14346796 | NO ACCESS, NEXT ACCESS: 08.07.2019 | [5 empty] | CLOSED
8950 | DH560 | CO-CO | TAI-005461218 | TAI-005461218 | NO ACCESS, NEXT ACCESS: 08.07.2019 | [5 empty] | CLOSED
8950 | DA999 | QN-NC | 14346796 | Scratch on AFT Fuselage sec. 19 RH | 07 06 2019 THC5G6 - CO TAI-005461218 is fully signed |  | Next access H241-1 on 08.07 - 11.07 S1 | work done, NC and folio will be closed after final paint. |  |  | CLOSED 18.07.2019
8951 | DH560 | OW-F5 | DH560-0003-005 | TAI QAR N008813 AIRBUS REF. NC 14306239 | Linked to Paint Para D53TAI198951003B |  | In Kl rung mit Paintshop - Arbeit erledigt. Nur ein Stempel zur Dokumentation fehlt. Status Schlie ung bis morgen | AIRBUS RESPONSIBILTY | KATERINA WILL HELP FOR CLOSURE, MAIL SENT. PAINT SHOP ISSUE | closed
8965 | DH620 | OW-F5 | DH620-0003-001 | 18D534-80505-069EX-GC2 Green Card Operation DTS Change | 24 06 2019 THB3W5 - no rework in the A C necessary information by Tayfun Celik |  | Mods expected to be deleted by Airbus within this week. Then TAI will close folio. | AIRBUS RESPONSIBILTY | WE ARE WAITING REBECA TO DELETE MODS, FATIH SENT E-MAIL
8965 | DH620 | OW-F5 | DH620-0003-001 | 18D534-80505-069EX-GC2 Green Card Operation DTS Change | 24 06 2019 THB3W5 - no rework in the A C necessary information by Tayfun Celik |  | Mods expected to be deleted by Airbus within this week. Then TAI will close folio. | AIRBUS RESPONSIBILTY | WE ARE WAITING REBECA TO DELETE MODS, FATIH SENT E-MAIL | CLOSED
8969 | DA999 | QN-NC | 14348106 | in acc. to EQLB SA.8969-0013 | Mapping to be done by QS |  | Access in 246 2 RH on 04.07. S2 WP | accepted as is, NC and folio to be closed. |  |  | CLOSED 18.07.2019
9000 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N009443 AIRBUS REF. NC 14308789 | Kratzer an C65-C66 P 9-P 10 und P 6-P 7 RH C68-C70 P15-P16 LH RH |  | abgearbeitet mit NC14308789 | JOB DONE | WAITING PARA FROM AAA | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9042 | DH550 | QN-NC | 14346916 | D-Inc DAS QR1 Dent |  |  | DASQR1 C64 P19-20 LH Delle Beule MAP Entscheidung ausstehend | ASK AAA |  |  | CLOSED
9042 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | AAA Resp. |  |  | CLOSED 17.07.2019
9042 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  |  | Ok by TAI |  |  | CLOSED 17.07.2019
9042 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N012772 AIRBUS REF. NC 14346916 | C64 P19-20 LH Delle Beule - TAI-005466579 |  |  | Ok by TAI |  |  | CLOSED 17.07.2019
9051 | DA999 | QN-NC | 14364872 | Service Door RH verformt | ABS Resp. |  | NC already closed returned to originator. |  |  |  | CLOSED
9070 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH mail -- install window Frame sealing |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | TAI wf access | WINDOW FRAME MODIFICATION |  | CLOSED 17.07.2019
9070 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH mail -- install window Frame sealing |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | TAI will work 12.07.2019 | WINDOW FRAME MODIFICATION |  | CLOSED 17.07.2019
9073 | DH550 | QN-NC | 14354863 | Inc DAS QR39 Dent | 04 06 2019 th67ww - C64 LH P19-P20 Dent in Outer Skin |  | C64 LH P19-P20 Dent in Outer Skin | NO PLAN | CONTROL
9073 | DH000 | QN-NC | 14363291 | 5 1 Bohrung kollidiert mit Clip | 12 06 2019 th67ww - C65 P3-4 RH 5 1 mm Bohrung kollidiert mit Clip |  | C65 P3-4 RH 5 1 mm Bohrung kollidiert mit Clip | AAA Resp. | CONTROL |  | CLOSED
9074 | DA999 | QN-NC | 14381001 | PPC dent on skin Sec. 19 RH |  |  | Next access H14W- Rest4 OSW 04.09 - 09.09 S1 | NO ACCESS, NEXT ACCESS: 04.08.2019 - 09.08.2019 | CONTROL | closed
9076 | DH000 | QN-NC | 14362404 | PCC Kratzer in der Aussenhaut |  |  | TAI AAA waiting for NDT. EoW 05.07 | NO PLAN | CONTROL | closed
9079 | DH000 | QN-NC | 14348414 | Damage at section 19 | C73 LH RH P24-P27 Sealant and paint from Cleat cracked Cleat C73 RH P25-P26 bent |  | Tolga BALCI Katerina SLUDNAYA NC still in exchange | JOB DONE, NC CLOSED FOLIO TO BE CLOSED. | NC FROM DH000, AIRBUS WILL CLOSE THIS NC | closed
9079 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N012132 AIRBUS REF. NC 14348414 | C73 LH RH P24-P27 Sealant and paint from Cleat cracked Cleat C73 RH P25-P26 bent |  | Thomas REIMANN Peter WEIGEL AC ist im Station 35 bitte die Airbeit plannen und EOW geben. Oner SOYER Bilal DEMIR | JOB DONE, NC CLOSED FOLIO TO BE CLOSED. |  | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9082 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N009498 AIRBUS REF. NC 14302284 | Chaffing marks on outer skin C65 to C64 P 4-P 5 RH |  | TAI D-Inc DAS QR01 RUAG impact | JOB DONE | NC, QAR AND FOLIO TO BE CLOSED |  | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9082 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N009498 AIRBUS REF. NC 14302284 | Chaffing marks on outer skin C65 to C64 P 4-P 5 RH |  | TAI D-Inc DAS QR01 RUAG impact | JOB DONE | NC, QAR AND FOLIO TO BE CLOSED | CLOSED | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9092 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N010797 AIRBUS REF. DR400073450 | TAI wf co. |  | CONTROL |  |  |  | CLOSED
9092 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | TAI wf MAP disp. | WINDOW FRAME MODIFICATION |  | CLOSED 17.07.2019
9093 | DH000 | QN-NC | 14380300 | EQLB SA.9093-0039 |  |  |  | NO PLAN | CONTROL | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9093 | DH630 | OW-F5 | DH630-0003-002 | TAI QAR N014349 AIRBUS REF. NC 14380300 | AAA Resp. |  |  | 15.07.2019
9095 | DH000 | QN-NC | 14379139 | Struktur BU passt nicht zur BUAusr stung | 1. Kompressorbock an C65-66 p40-42 R H Kein Kompressor 2. Falscher Halter an QT 65 R H |  |  | NO PLAN | CONTROL | closed
9106 | DH550 | QN-NC | 14352433 | Inc DAS QR1 Impact |  |  | TAI Inc DAS QR1 Impact C64 - C65 LH P22-P23 | NEW |  | CLOSED
9106 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N012781 AIRBUS REF. NC 14352433 | NEW 09.07 | [5 empty] | CLOSED
9108 | DH000 | QN-NC | 14375545 | EQLB 9108-0004 | C65-C66 P38-P42LH |  | job done by TAI NC closed. folio to be closed. | AIRBUS RESPONSIBILTY | DH000 FOLIO POINT, WE CANT CLOSE, AIRBUS WILL CLOSE AFTER OPERATIONS. | closed
9108 | DH000 | CO-CO | TH-005457090 | TH-005457090 | C64 65 P 24 RH. Fehlerhafter Stringer - TH-005457090 inP |  | Shardul JOSHI need stamped para from Airbus | AIRBUS RESPONSIBILTY | C64/65 P'24 RH. Fehlerhafter Stringer |  | CLOSED
9108 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012240 AIRBUS REF. NC 14346528 | C64 65 P 24 RH. Fehlerhafter Stringer |  | Shardul JOSHI need stamped para from Airbus | AIRBUS RESPONSIBILTY | C64/65 P'24 RH. Fehlerhafter Stringer |  | CLOSED 18.07.2019
9115 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N014118 AIRBUS REF. NC 14374017 |  |  | job done NC closed folio to be closed. | NEW
9115 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N014119 AIRBUS REF. NC 14375580 |  |  | job done NC closed folio to be closed. | NEW
9116 | DH000 | QN-NC | 14354484 | EQLB SA.9116-0013 | Dep SA.9116-0013 |  | TAI AAA Work i.P. EoW 18.06 | AIRBUS RESPONSIBILTY | DH000 FOLIO POINT, WE CANT CLOSE, AIRBUS WILL CLOSE AFTER OPERATIONS. | CLOSED
9118 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012242 AIRBUS REF. NC 14346552 | 02 07 2019 THB3W5 - will be closed soon by TAI |  | WF stamped para from airbus | AIRBUS RESPONSIBILTY | WF stamped para from airbus
9118 | DH000 | QN-NC | 14345856 | Damage at section 19 | Inflow QG-I |  | Katerina Sludnaya Kannst du bitte pushen das PAG noch auf St.40 fertig wird | PAG RESPONSIBILITY | CONTROL |  | CLOSED 17.07.2019
9118 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N011841 AIRBUS REF. NC 14345856 | QG-inflow |  | PAG next access 04.0-05.07 Thomas REIMANN Please provide status | PAG RESPONSIBILITY | CONTROL |  | CLOSED 18.07.2019
9121 | DH550 | QN-NC | 14331078 | Inc DAS QR1 Impact | JOB DONE |  | JOB DONE BY TAI |  |  |  | CLOSED
9121 | DH550 | QN-NC | 14331111 | Inc DAS QR1 Scratch | JOB DONE |  | JOB DONE BY TAI |  |  |  | CLOSED
9121 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N010861 AIRBUS REF. NC 14331111 |  |  | TAI Inc DAS QR1 Scratch | Job done by TAI, NC closed, folio to be closed. |  |  | CLOSED
9121 | DH660 | OW-F5 | DH660-0003-002 |  |  |  |  | FOLIO DETAILS ASKED TO ANKARA |  |  | CLOSED
9123 | DH550 | QN-NC | 14386259 | Inc DAS QR41 damaged sealing |  |  |  | AAA RESPONSIBILTY |  |  | CLOSED
9135 | DH000 | QN-NC | 14358453 | Damage at section 19 | PAG RESPONSIBILITY |  | Job must be finished. |  |  |  | CLOSED
9135 | DH560 | OW-F5 | DH560-0003-004 | TAI QAR N014247 AIRBUS REF. NC 14375586 | C73 - C74 LH RH sealing on bonding brackets missing -- work done 14375586 closed |  |  | ASK ONER |  | closed
9139 | DH000 | QN-NC | 14376488 | PCC 1 Kratzer in der Aussenhaut | RH C66-65 P 9-P 10 NDT done - rework TAI done - will be closed by QS structure |  | Job done NC closed. Folio to be closed. P5 | ASK ONER |  | closed
9141 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH sealant au en offen mail |  | Katerina Sludnaya Please give Feedback. PW | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED 17.07.2019
9141 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH sealant au en offen mail |  | Katerina Sludnaya Please give Feedback. PW | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED 17.07.2019
9149 | DH560 | QN-NC | 14340958 | Damage at section 19 | - C73 P 20-P 21 RH and from P 24 to P 31 RH the Sealant and paint from Cleat cracked |  | New access slot 08.07 in ST40 H14 L1 | NO ACCESS, NEXT ACCESS: 08.07.2019 |  | closed
9149 | DH000 | QN-NC | 14356658 | PCC Kratzer C75 - C76 P9 - P10 LH | 21 06 2019 THC5G6 - CO TAI-005465009 fully signed |  | TAI work will be perfomed in St40 08.07 | NO ACCESS, NEXT ACCESS: 08.07.2019
9149 | DH000 | QN-NC | 14356658 | PCC Kratzer C75 - C76 P9 - P10 LH | 21 06 2019 THC5G6 - CO TAI-005465009 fully signed |  | TAI work will be perfomed in St40 08.07 | NO ACCESS, NEXT ACCESS: 08.07.2019 |  | CLOSED
9149 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N012232 AIRBUS REF. NC 14340958 | - C73 P 20-P 21 RH and from P 24 to P 31 RH the Sealant and paint from Cleat cracked |  | PAG Waiting for Access on AC. Next possible access 05.07 | NO ACCESS, NEXT ACCESS: 08.07.2019 |  | CLOSED
9149 | DH560 | CO-CO | TAI-005465009 | TAI-005465009 | Kratzer C75 - C76 P9 - P10 LH |  | Work to be performed by TAI on 08.07 | NO ACCESS, NEXT ACCESS: 08.07.2019 |  |  | CLOSED
9149 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N012898 AIRBUS REF. NC 14356658 | Kratzer C75 - C76 P9 - P10 LH |  | TAO wprk planned for 08.07 | NO ACCESS, NEXT ACCESS: 08.07.2019 |  |  | CLOSED 17.07.2019
9154 | DH550 | QN-NC | 14362800 | D-Inc DAS QR1 Stringer cap | Inflow QG-I |  | C64 -C65 P 24 RH | NO PLAN | CONTROL
9154 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012753 AIRBUS REF. DR 400073960 | DASL - C64-C65 P 24 RH Falscher Stringer eingebaut - PARA D 53 TAI 18 9154 001 B 132 000. WO 117420973. |  | TAI QAR N012753 AIRBUS REF. DR 400073960 | NO PLAN | CONTROL | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9165 | DH550 | QN-NC | 14370230 | Inc DAS QR39 Dent | 24 06 2019 THC6BS - C64 P19-20 LH Beule im Hautfeld |  | AAA will perform the job | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9165 | DH000 | QN-NC | 14373354 | Besch digung der Oberfl che Fase Rille | 24 06 2019 THC6BS - C64-65LH P7-8 Fremdbesch digung in der Aussenhaut |  | Shardul JOSHI this NC doesnt exist in SAP PAC | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9165 | DH000 | QN-NC | 14376865 | Besch digung an der Au enhaut | Inflow QG-I |  | job done by TAI NC closed. folio to be closed. | job done by TAI NC closed. folio to be closed. |  |  | CLOSED
9167 | DH000 | QN-NC | 14364034 | Kratzer oder Bearbeitungsriefen | NO ACCESS |  | WF FOR PARA | 15.07.2020
9167 | DH000 | QN-NC | 14364079 | Inkorrekte Form | AIRBUS RESPONSIBILTYONSIBILTY |  |  | 15.07.2021
9167 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012514 AIRBUS REF. DR 400073960 |  |  | Waiting for stamped para from RUAG | NEW
9167 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012562 AIRBUS REF. DR 400074087 | NEW 09.07 |  |  | 15.07.2022
9167 | DH620 | CO-CO | TAI-005460967 | TAI-005460967 | No involvement hangar 8 SA - 09.07.2019 |  |  | NEW
9170 | DH000 | QN-NC | 14352558 | Inkorrekte Form | Inflow QG-i |  | No access before St.41. | NO PLAN | CONTROL | closed
9170 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N012583 AIRBUS REF. NC 14353233 | C73 P24-P25 LH RH. Sealant and paint from Cleat cracked. |  | Stamped PARA provided by PAG. Folio to be closed | NO PLAN | CONTROL | closed
9170 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N014356 AIRBUS REF. NC 14378838 |  |  |  | NO PLAN | CONTROL | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9170 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N014356 AIRBUS REF. NC 14378838 |  |  | Tayfun CELIK close FoliO point NC is already closed | NEW 10.07 |  | CLOSED
9170 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012447 AIRBUS REF. NC 14352558 | C64-C65 P24 RH. Falscher Stringer verbaut - TAI-005460966. |  | TAI PARA PARA D 53 TAI 18 9170 001 B 132 000 provided to AiB to perform the Job | NO PLAN | CONTROL | closed
9170 | DH620 | CO-CO | TAI-005460966 | TAI-005460966 | C64-C65 P24 RH. Falscher Stringer verbaut - TAI-005460966. |  | TAI | NO PLAN | CONTROL | closed
9170 | DH000 | QN-NC | 14352558 | Inkorrekte Form | Inflow QG-i |  | WOrk done. Stamped PARA sent to TAI. Tolga BALCI please close the folio | AIRBUS RESPONSIBILTY |  |  | CLOSED 18.07.2019
9170 | DH620 | CO-CO | TAI-005460966 | TAI-005460966 | C64-C65 P24 RH. Falscher Stringer verbaut - TAI-005460966. |  | WORK DONE | AIRBUS RESPONSIBILTY |  |  | CLOSED 18.07.2019
9170 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N012447 AIRBUS REF. NC 14352558 | C64-C65 P24 RH. Falscher Stringer verbaut - TAI-005460966. |  | WOrk done. Stamped PARA sent to TAI.folio to be closed | AIRBUS RESPONSIBILTY |  |  | CLOSED 18.07.2019
9171 | DH550 | QN-NC | 14353693 | Inc DAS QR1 Joggle position | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | Katerina Sludnaya | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed
9171 | DH550 | QN-NC | 14353693 | Inc DAS QR1 Joggle position | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | Katerina Sludnaya | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed | CLOSED
9171 | DH000 | QN-NC | 14356722 | Kratzer | C64 - C65 RH P6 - P7 scratch t 0 12mm -- 1.NDT done -- TAI-005472155 polish out |  | TAI AAA work done. CO fully signed. NC will be closed today. FW in TAI-005472155 to be crossed out by TAI | JOB DONE BY AAA | ONER SENT MAIL FOR QAR AND FOLIO CLOSURE | closed
9171 | DH000 | QN-NC | 14380178 | PCC Beule an der Regenrinne LH | C67 - C68 LH P8 - P9 dent on rain gutter t -0 2mm -- 1.NDT done -- PARA to dent doctor 117494815 |  | TAI AAA waiting for NDT access St42 on 12.07 | NO ACCESS, NEXT ACCESS: 12.07.2020
9171 | DH000 | QN-NC | 14380178 | PCC Beule an der Regenrinne LH | C67 - C68 LH P8 - P9 dent on rain gutter t -0 2mm -- 1.NDT done -- PARA to dent doctor 117494815 |  | TAI AAA waiting for NDT access St42 on 12.07 | NO ACCESS, NEXT ACCESS: 12.07.2020 |  | CLOSED
9171 | DH000 | QN-NC | 14383669 | Kratzer Aussenhaut C69-C70 | C69 - C70 RH P31 - P32 scratch |  | TAI AAA MAP statement available. Rework planned depending on the access to the area ST42 L 1 H14 - 12.07. | NO ACCESS, NEXT ACCESS: 12.07.2019
9171 | DH000 | QN-NC | 14383669 | Kratzer Aussenhaut C69-C70 | C69 - C70 RH P31 - P32 scratch |  | TAI AAA MAP statement available. Rework planned depending on the access to the area ST42 L 1 H14 - 12.07. | NO ACCESS, NEXT ACCESS: 12.07.2019 |  | CLOSED
9171 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9171 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012679 AIRBUS REF. NC 14353693 | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | TAI | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed
9171 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012679 AIRBUS REF. NC 14353693 | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | TAI | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed | CLOSED
9171 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012679 AIRBUS REF. NC 14353693 | NEW 12.07 | [5 empty] | CLOSED
9171 | DH620 | OW-F5 | DH620-0003-003 | TAI QAR N012886 AIRBUS REF. NC 14356722 | C64 - C65 RH P6 - P7 scratch t 0 12mm -- 1.NDT done -- TAI-005472155 polish out |  | C64-65 Kratzer P6-7 RH | JOB DONE BY AAA | ONER SENT MAIL FOR QAR AND FOLIO CLOSURE |  | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9171 | DH620 | OW-F5 | DH620-0003-003 | TAI QAR N012886 AIRBUS REF. NC 14356722 | C64 - C65 RH P6 - P7 scratch t 0 12mm -- 1.NDT done -- TAI-005472155 polish out |  | C64-65 Kratzer P6-7 RH | JOB DONE BY AAA | ONER SENT MAIL FOR QAR AND FOLIO CLOSURE | CLOSED | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9171 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9171 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N011698 AIRBUS REF. DR 400073823 |  |  | Pascal JUNG Please provide status. | NO PLAN | TAI QAR N011698 AIRBUS REF. DR 400073823
9171 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N011698 AIRBUS REF. DR 400073823 |  |  | Pascal JUNG Please provide status. | NO PLAN | TAI QAR N011698 AIRBUS REF. DR 400073823 | CLOSED
9171 | DH620 | CO-CO | TAI-005461049 | TAI-005461049 | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | TAI Waiting for Stamped PARA D 53 TAI 18 9171 001 B 132 000 to struc | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed
9171 | DH620 | CO-CO | TAI-005461049 | TAI-005461049 | C64 - C65 RH P24 Stringer with wrong shape installed -- install Stringer with other measurments for Drilling and fill the GAP between Skin and Stringer with sealing -- PARA D 53 TAI 18 9171 001 B 132 000 to struc |  | TAI Waiting for Stamped PARA D 53 TAI 18 9171 001 B 132 000 to struc | AIRBUS RESPONSIBILTY | WF STAMPED PARA FROM AIRBUS. C64 - C65 RH P24 Stringer with wrong shape installed | CLOSED
9171 | DH620 | CO-CO | TAI-005472155 | TAI-005472155 | C64 - C65 RH P6 - P7 scratch t 0 12mm -- 1.NDT done -- TAI-005472155 polish out |  | ACC. Waiting FW to be crossed out | JOB DONE BY AAA | Waiting FW to be crossed out
9171 | DH620 | CO-CO | TAI-005472155 | TAI-005472155 | C64 - C65 RH P6 - P7 scratch t 0 12mm -- 1.NDT done -- TAI-005472155 polish out |  | ACC. Waiting FW to be crossed out | JOB DONE BY AAA | Waiting FW to be crossed out | CLOSED
9173 | DH000 | QN-NC | 14380874 | Annietmutter defekt | C70 RH P20 anchor nut damage |  |  | NO PLAN | ASK ONER | closed
9173 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N014513 AIRBUS REF. NC 14380874 | C70 RH P20 anchor nut damage |  |  | NO PLAN | ASK ONER | CLOSED
9173 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012430 AIRBUS REF. DR 400073960 | C64 - C65 RH P24 wrong Stringer wrong shape -- TAI-005461168 install Stringer out of nominal Position and fill the gap between Skin and Stringer with sealant |  |  | NO PLAN | ASK ONER | CLOSED
9173 | DH620 | CO-CO | TAI-005461168 | TAI-005461168 | C64 - C65 RH P24 wrong Stringer wrong shape -- TAI-005461168 install Stringer out of nominal Position and fill the gap between Skin and Stringer with sealant |  | TAI Stringer C64-C65 P 24 RH | NO PLAN | ASK ONER | CLOSED
9173 | DH550 | QN-NC | 14359872 | D-Inc DAS QR1 Stringer cap | C64 - C65 RH P24 wrong Stringer wrong shape -- TAI-005461168 install Stringer out of nominal Position and fill the gap between Skin and Stringer with sealant |  | DASL C64-65 P24RH Innen und Au en. Falsche Stringerlage. Kupplung Pos.0019 und St tzwinkel Pos.0055 sind nicht eingebaut. NC14359872 | JOB DONE | JOB DONE BY DASL, PARA PROVIDED |  | CLOSED
9173 | DH000 | QN-NC | 14371055 | Fensterrahmen zerkratzt | C64 - C65 LH P14 - P15 scratch on window Frame -- polish out done -- Paint touch up in Paint shop |  | TAI Section 18 C64 C65 P14-P18 Main Deck LH Fenster zerkratzt | NO NC IN POSTBOX |  |  | CLOSED 18.07.2019
9174 | DH560 | OW-F5 | DH560-0003-001 | flexible hose will change because of the reallocation from MSN 9332 to |  |  | TAI | ASK ONER | ASK ONER
9174 | DH560 | OW-F5 | DH560-0003-001 | flexible hose will change because of the reallocation from MSN 9332 to |  |  | TAI | ASK ONER | ASK ONER | CLOSED
9174 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N014237 AIRBUS REF. NC 14375412 |  |  | TAI | ASK ONER | ASK ONER
9174 | DH560 | OW-F5 | DH560-0003-003 | TAI QAR N014237 AIRBUS REF. NC 14375412 |  |  | TAI | ASK ONER | ASK ONER | CLOSED
9197 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EFFECTIVE ACCORDING TO DTS REV.DT. ALSO IN NORMAL | Inflow QG-I |  | Status Who is performing work | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9197 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EFFECTIVE ACCORDING TO DTS REV.DT. ALSO IN NORMAL | Inflow QG-I |  | Status Who is performing work | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9200 | DH000 | QN-NC | 14363292 | Farbabplatzer im T rrahmen | Inflow Qg-I |  | Ham. Halter demontiert. | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY
9200 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | Inflow QG-I |  | Danilo Topp | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9200 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | Inflow QG-I |  | Danilo Topp | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | CLOSED
9200 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | Inflow QG-I |  | Danilo Topp | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9200 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | Inflow QG-I |  | Danilo Topp | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | CLOSED
9201 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N012148 AIRBUS REF. DR 400073929 | QG-inflow |  | work done |  | QAR WAS VOIDED, AND FOLIO WAS DELETED | closed | oNER SENT MAIL FOR FOLIO CLOSURE. 06.07 DILARA.
9204 | DH660 | OW-F5 | DH660-0003-002 | TAI QAR N014641 AIRBUS REF. NC 14381967 |  |  | TAI DASR35 C65 P20-P22LH RH kaum Kitt zw. Clip u. Aussenhaut | Job done by TAI, NC closed, folio to be closed. | JOB DONE BY TAI |  | CLOSED
9204 | DH000 | QN-NC | 14381967 | kaum Kitt zw. Clip u. Aussenhaut |  |  | DASR35 C65 P20-P22LH RH kaum Kitt zw. Clip u. Aussenhaut | Job done by TAI, NC closed, folio to be closed. | JOB DONE BY TAI |  | CLOSED 18.07.2019
9206 | DH000 | QN-NC | 14360675 | Inkorrekte Form | Inflow Qg-I |  | Katerina SLUDNAYA Katerina Sludnaya WF stamped para from Airbus | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY
9206 | DH000 | QN-NC | 14360675 | Inkorrekte Form | Inflow Qg-I |  | Katerina SLUDNAYA Katerina Sludnaya WF stamped para from Airbus | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | CLOSED
9206 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N012318 AIRBUS REF. DR 400073990 | Falscher Stringer an C64 - C65 P24 RH PARA an HAM PARA D53TAI1892061B |  | WF stamped para from Airbus | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY
9206 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N012318 AIRBUS REF. DR 400073990 | Falscher Stringer an C64 - C65 P24 RH PARA an HAM PARA D53TAI1892061B |  | WF stamped para from Airbus | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | CLOSED
9208 | DH000 | QN-NC | 14385751 | Delle Beule | Delle Beule an C66-C67 P 40-P 42 RH |  | TAI Feedback | job done NC closed. folio to be closed after co. Creation. | WF PARA |  | CLOSED 17.07.2019
9208 | DH000 | QN-NC | 14385688 | Delle Beule | Delle Beule C64-C65 P34-P36 1. NDT fertig |  | No work in AC only docu | job done NC closed. folio to be closed after co. Creation. | WF MAP DISP: |  | CLOSED 18.07.2019
9208 | DH000 | QN-NC | 14388840 | Bohrung und Strukturwinkel fehlt |  |  | EXCH: TAI | NO PLAN |  |  | CLOSED 18.07.2019
9211 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH |  | Fenster MOD | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9211 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH |  | Fenster MOD | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9211 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH660 MOD25020 Fenster Sekt.18 C64-C65 LH |  | Fenster MOD | AIRBUS RESPONSIBILTY |  |  | CLOSED
9211 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | DH620 MOD20863 Fenster Sekt.18 C64-C65 RH |  | Fenster MOD | AIRBUS RESPONSIBILTY |  |  | CLOSED
9212 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  |  | CLOSED 17.07.2019
9212 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY |  |  | CLOSED 17.07.2019
9213 | DH560 | QN-NC | 14382465 | Damage at section 19 | PAG RESPONSIBILTYONSIBILTY |  |  | 15.07.2025
9213 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION | 15.07.2023
9213 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION | 15.07.2024
9215 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9215 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9218 | DH560 | QN-NC | 14385898 | Damage at section 19 | TAI |  | WILL BE WORKED 12.07 |  |  |  | CLOSED
9218 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9218 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9218 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N014834 AIRBUS REF. NC 14385898 | 12 07 2019 TH67HG - C73 P20-29 RH P24-29 LH Sealant and paint from Cleat cracked |  | C73 P20-29 RH P24-29 LH Sealant and paint from Cleat cracked | NO PLAN |  |  | CLOSED
9219 | DH000 | QN-NC | 14379601 | Scratch |  |  | C65-C66 P8-P9 LH Scratch detected on outer skin rework from TAI necessary | NO PLAN | ASK ONER
9219 | DH000 | QN-NC | 14379601 | Scratch | AAA RESPONSIBILTYONSIBILTY |  |  | 15.07.2026
9219 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N014403 AIRBUS REF. NC 14379601 |  |  | Sec. 18 C65-C66 P8-P9 LH work line becasue of ref. NC 14379601 scatch on outer skin rework TAI necessary | NO PLAN | ASK ONER
9219 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N014403 AIRBUS REF. NC 14379601 | new 11.07 |  |  | 15.07.2027
9220 | DH000 | QN-NC | 14375714 | Kratzer oder Bearbeitungsriefen |  |  | Sec. 18 C64-C66 P17-P22 LH RH scratchs in outer skin rework from TAI necessary | NO PLAN | ASK ONER | closed
9220 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9220 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9223 | DH000 | QN-NC | 14359324 | Fehlbohrung | Inflow QG-I |  | TAI planning new part installation on 08 July S1. | PLANNED FOR 07.07.2019 SUNDAY, PART EXCHANGE. | ASK ONER | closed
9224 | DH000 | QN-NC | 14376881 | eQLB 9224-0001 | AIRBUS RESPONSIBILTY |  | DH000 FOLIO POINT, WE CANT CLOSE, AIRBUS WILL CLOSE AFTER OPERATIONS. |  |  |  | CLOSED
9224 | DH000 | QN-NC | 14376881 | eQLB 9224-0001 | AIRBUS RESPONSIBILTY |  | DH000 FOLIO POINT, WE CANT CLOSE, AIRBUS WILL CLOSE AFTER OPERATIONS. |  |  |  | CLOSED
9225 | DH000 | QN-NC | 14380680 | Kratzer |  |  | C68 RH P19 P20 Kratzer am T rrahmen TAI | AAA RESPONSIBILTYONSIBILTY |  |  | CLOSED
9225 | DH560 | OW-F5 | DH560-0003-002 | TAI QAR N014466 AIRBUS REF. NC 14358564 |  |  | Sec 19 work line for NC 14358564 eQLB SA.9060-0049 rod is damaged rework TAI necessary | NO PLAN | WILL BE CHECKED ON MONDAY |  | CLOSED
9225 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N014395 AIRBUS REF. NC 14380680 |  |  | work done only docu NC14380680 closed | NO PLAN | WILL BE CHECKED ON MONDAY |  | CLOSED
9225 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N014357 AIRBUS REF. NC 14379230 |  |  | Sec. 19 C73 P24-P25 LH RH work line for NC 14379230 sealant and paint from cleat cracked rework TAI necessary | NO PLAN | WILL BE CHECKED ON MONDAY |  | CLOSED
9225 | DH000 | QN-NC | 14379230 | Damage at section 19 |  |  | TAI | NO PLAN |  |  | CLOSED
9227 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014367 AIRBUS REF. DR 400074829 |  |  |  | NEW |  | CLOSED
9227 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED 18.07.2019
9227 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED 18.07.2019
9227 | DH550 | QN-NC | 14388721 | Inc DAS QR41 damaged sealing |  |  |  | NO PLAN |  |  | CLOSED 18.07.2019
9229 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9229 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9229 | DH000 | QN-NC | 14388441 | Damage at section 19 |  |  | PAG H.3 H29 Slot noetig oder in Ausr stung abarbeitbar - H1-4 nicht aba | NO PLAN |  |  | CLOSED
9229 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N014988 AIRBUS REF. NC 14388441 |  |  | Sec. 19 C73 P24-P26 LH RH work line because of NC 14388441 sealant and paint from cleat cracked rework TAI necessary | NO PLAN |  |  | CLOSED
9231 | DH560 | QN-NC | 14388629 | Damage at section 19 | NEW 12.07 |  |  | 15.07.2028
9232 | DH000 | QN-NC | 14377194 | Kopf-Verbindungsteil liegt nicht plan an |  |  | TAI C67 P6-P7 LH RH Niet berstand | NEW
9233 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 02 07 2019 THC6BS - Fenster MOD |  | Fenster MOD | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9233 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 03 07 2019 THC6BS - Fenster MOD |  | Fenster MOD | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9233 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 02 07 2019 THC6BS - Fenster MOD |  | Fenster MOD | AIRBUS RESPONSIBILTY |  |  | CLOSED
9233 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | 03 07 2019 THC6BS - Fenster MOD |  | Fenster MOD | AIRBUS RESPONSIBILTY |  |  | CLOSED
9235 | DH000 | QN-NC | 14387092 | Damage at section 19 | TAI |  | WILL BE WORKED 12.07 | 15.07.2029
9235 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N014829 AIRBUS REF. NC 14387092 | new 11.07 |  |  | 15.07.2030
9235 | DH560 | OW-F5 | DH560-0003-001 | TAI QAR N014829 AIRBUS REF. NC 14387092 |  |  | job done NC closed. folio to be closed | new 15.07.2019 |  |  | CLOSED 18.07.2019
9239 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EFFECTIVE ACCORDING TO DTS REV.DT. ALSO IN NORMAL | Sealant herstellen PARA an HAM D534.CH.9239.01.0A |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9239 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EFFECTIVE ACCORDING TO DTS REV.DT. ALSO IN NORMAL | Sealant herstellen PARA an HAM D534.CH.9239.01.0A |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION
9243 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9243 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Shardul JOSHI Katerina SLUDNAYA Waiting for stamped para from Airbus | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION |  | CLOSED
9244 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013206 AIRBUS REF. DR 400074375 |  |  | Kl rung | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY
9244 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013206 AIRBUS REF. DR 400074375 |  |  | Kl rung | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | CLOSED
9247 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014595 AIRBUS REF. DR 400074952 |  |  |  | NO PLAN |  |  | CLOSED 18.07.2019
9248 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014366 AIRBUS REF. DR 400074819 |  |  |  | NEW |  | CLOSED
9250 | DH000 | QN-NC | 14364491 | Inkorrekte Form | AIRBUS RESPONSIBILTYONSIBILTY |  |  | 15.07.2031
9250 | DH620 | OW-F5 | DH620-0003-003 | TAI QAR N012515 AIRBUS REF. DR 400073960 | Falscher Stringer an C64-C65 P 24 RH montiert |  | NC closed. Folio to be closed | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9250 | DH620 | CO-CO | TAI-005461166 | TAI-005461166 | Falscher Stringer an C64-C65 P 24 RH montiert. |  |  | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9252 | DH000 | QN-NC | 14381726 | Kratzer oder Bearbeitungsriefen |  |  | C66 P21-P22 RH scatches on dorr frame rework TAI necessary | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9252 | DH000 | QN-NC | 14381844 | Oberfl chenschutz |  |  | C66-C68 P9-P11 LH surface protection is damaged on door frame rework TAI necessary | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9252 | DH550 | QN-NC | 14382061 | Dent on Frame 65 STR05-07 RH |  |  | Sec. 18 C65 P5-P7 RH dents on frame and gap between fram an clip rework TAI necessary | NO PLAN | ASK ONER | closed
9252 | DH000 | QN-NC | 14382326 | Kratzer oder Bearbeitungsriefen |  |  | Sec. 18 C64-C65 P22-P23 RH scatch on outer skin rework TAI necessary | NO PLAN | ASK ONER | closed
9252 | DH000 | QN-NC | 14382810 | Mangelhafter Aufbau der Versiegelung |  |  | Sec. 18 C66-C68 P7-P10 LH damage of surface protection on door frame rework TAI necessary | NO PLAN | ASK ONER | closed
9252 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N014033 AIRBUS REF. NC 14372127 |  |  | work line for NC 14372127 | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed | ONER SENT MAIL FOR FOLIO CLOSURE. 06.07
9252 | DH000 | QN-NC | 14382810 | Mangelhafter Aufbau der Versiegelung | 16 07 2019 th67s0 - Sec. 18 C66-C68 P7-P10 LH damage of surface protection on door frame |  | Sec. 18 C66-C68 P7-P10 LH damage of surface protection on door frame rework TAI necessary | YENI 17.07.2019 |  |  | CLOSED 18.07.2019
9253 | DH000 | QN-NC | 14367490 | Kopf-Verbindungsteil liegt nicht plan an | Inflow QG-I |  | job will be performed by AAA. EOW 01.07 | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9253 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N013899 AIRBUS REF. NC 14367490 | Kopf-Verbindungsteil liegt nicht plan an C67 P 6-P 7 RH Deckblech am Torsionskasten |  | Sec. 18 C67 P6-P7 RH work line for NC 14367490 because of gab between rivet and frame inside | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY
9253 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N013899 AIRBUS REF. NC 14367490 | Kopf-Verbindungsteil liegt nicht plan an C67 P 6-P 7 RH Deckblech am Torsionskasten |  | Sec. 18 C67 P6-P7 RH work line for NC 14367490 because of gab between rivet and frame inside | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | CLOSED
9256 | DH000 | QN-NC | 14386916 | Damage on Doorframe sect. 18 RH | NEW 09.07 | [5 empty] | CLOSED
9256 | DH000 | QN-NC | 14386916 | Damage on Doorframe sect. 18 RH | NEW 09.07 | [5 empty] | CLOSED
9256 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION |  |  |  | CLOSED
9256 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION |  |  |  | CLOSED
9256 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N013207 AIRBUS REF. DR 400074207 | NOT IN TANDEM 07.07.2019 |  | WILL BE CHECKED ON MONDAY |  |  |  | CLOSED
9256 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N013207 AIRBUS REF. DR 400074207 | NOT IN TANDEM 07.07.2019 |  | WILL BE CHECKED ON MONDAY |  |  |  | CLOSED
9256 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION |  |  |  | CLOSED
9256 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION |  |  |  | CLOSED
9261 | DH000 | QN-NC | 14379619 | Kratzer oder Bearbeitungsriefen | AAA RESPONSIBILTYONSIBILTY |  |  | 15.07.2033
9261 | DH550 | OW-F5 | DH550-0003-001 | please check the GAP on the first joggle at stringer P 24 in the area of | NO PLAN |  | ASK ONER | 15.07.2032
9261 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013536 AIRBUS REF. DR 400074489 | NO PLAN |  | ASK ONER | 15.07.2035
9261 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N014440 AIRBUS REF. NC 14379619 | NO PLAN |  | ASK ONER | 15.07.2034
9261 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N014440 AIRBUS REF. NC 14379619 |  |  | TAI AAA will perform the job 12.07 | NEW 16.07.2019 |  |  | CLOSED
9261 | DH550 | OW-F5 | DH550-0003-001 | please check the GAP on the first joggle at stringer P 24 in the area of |  |  | Sec. 18 C65 P24 RH work line becasue of check the GAP on the first joggle at stringer rework TAI necessary | NEW 16.07.2019 |  |  | CLOSED
9261 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013536 AIRBUS REF. DR 400074489 |  |  | TAI | NEW 16.07.2019 |  |  | CLOSED
9261 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N014440 AIRBUS REF. NC 14379619 | Kratzer oder Bearbeitungsriefen an C68 P13 -P15 LH |  | The job is done and NC closed. TAI is informed to close Folio | YENI 17.07.2019 |  |  | CLOSED 17.07.2019
9261 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N013536 AIRBUS REF. DR 400074489 | Kl rung durch TAI erforderlich |  | TAI | YENI 17.07.2019 |  |  | CLOSED 18.07.2019
9264 | DH000 | QN-NC | 14384206 | Nietverbindung |  |  | TAI C67 P7 LH 1x RH 2x 3x Verbindungselement muss erneuert werden HAM Struktur hat keine Nacharbeit | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9264 | DH620 | OW-F5 | DH620-0003-001 | THE MOD 20863 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 RH work line for rework of window according MOD 20863 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9264 | DH620 | OW-F5 | DH620-0003-002 | TAI QAR N012606 AIRBUS REF. DR 400073960 |  |  | TAI | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9264 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. |  |  | Sec. 18 C64-C65 LH work line for rework of window according MOD 25020 | AIRBUS RESPONSIBILTY | WINDOW FRAME MODIFICATION | closed
9264 | DH000 | QN-NC | 14384206 | Nietverbindung |  |  | TAI C67 P7 LH 1x RH 2x 3x Verbindungselement muss erneuert werden HAM Struktur hat keine Nacharbeit | NO PLAN |  |  | CLOSED 18.07.2019
9271 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N012786 AIRBUS REF. NC 14351789 | NOT IN TANDEM 07.07.2019 |  | WILL BE CHECKED ON MONDAY | 15.07.2036
9271 | DH660 | OW-F5 | DH660-0003-001 | TAI QAR N012786 AIRBUS REF. NC 14351789 | 01 07 2019 TH67HG - The work is done and controlled For the following workflow name EX TAI SA |  | The work is done and controlled | NEW 16.07.2019 |  |  | CLOSED 18.07.2019
9274 | DH000 | QN-NC | 14371653 | Scratches Paint damage |  |  | TAI Besch digungen am T rrahmen C66-C68 P 12-P 15 RH. | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
9279 | DH000 | QN-NC | 14383109 | Verbindungselement falsch positioniert | AAA RESPONSIBILTYONSIBILTY |  |  | 15.07.2037
9279 | DH000 | QN-NC | 14383217 | Verbindungselement falsch positioniert | AAA RESPONSIBILTYONSIBILTY |  |  | 15.07.2038
9283 | DH000 | QN-NC | 14390734 | Scratch |  |  | Sec. 18 C66 P11-P12 LH scratch on door frame rework TAI necessary | AAA WILL PERFORM THE JOB | WF. MAP. DESP: |  | CLOSED
9296 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N013526 AIRBUS REF. DR 400074540 |  |  | TAI | NEW
9296 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014573 AIRBUS REF. DR 400074913 |  |  | TAI | NEW
9296 | DH570 | OW-F5 | DH570-0003-001 | TAI QAR N013526 AIRBUS REF. DR 400074540 |  |  | TAI | NO PLAN |  |  | CLOSED 18.07.2019
9296 | DH630 | OW-F5 | DH630-0003-001 | TAI QAR N014573 AIRBUS REF. DR 400074913 |  |  | TAI | NO PLAN |  |  | CLOSED 18.07.2019
9339 | DH000 | QN-NC | 14387198 | Damage in Outerskin Panel | TAI. |  | WF CONCESSION | 15.07.2039
9340 | DH000 | QN-NC | 14387055 | Besch digte Bohrungsfl che -kante |  |  | Sec. 18 C66 P18-P19 LH damage surface protection on door frame rework TAI necessary | NEW 10.07 |  | CLOSED
10001 | DH550 | QN-NC | 14370281 | Inc DAS QR30 Door frame |  |  | work done by TAI NC closed. Folio to be closed. | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
10001 | DH550 | QN-NC | 14370282 | Inc DAS QR1 Joggle position | WORK DONE BY AIRBUS |  | WF PARA | 15.07.2042
10001 | DH000 | QN-NC | 14374416 | Kratzer | AAA RESPONSIBILTYONSIBILTY |  |  | 15.07.2040
10001 | DH620 | OW-F5 | DH620-0003-001 | TAI QAR N013042 AIRBUS REF. DR 400073960 |  |  | TAI | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
10001 | DH660 | OW-F5 | DH660-0003-001 | THE MOD 25020 IS NOT EMBODIED. IT WILL BE PERFORMED AT NEXT STAGE. | AIRBUS RESPONSIBILTY |  | WINDOW FRAME MODIFICATION | 15.07.2041
10001 | DH620 | CO-CO | TAI-005465567 | TAI-005465567 |  |  | work done from HAM | NOT IN TANDEM 07.07.2019 | WILL BE CHECKED ON MONDAY | closed
10001 | DH000 | QN-NC | 14374416 | Kratzer |  |  | C66 LH P12 P21 Kratzer am T rrahmen TAI | NO PLAN |  |  | CLOSED 17.07.2019